# Weight Insight Mentoring Service (WIMS)

Service Definition and Implementation Plan

Title: WIMS - Service Definition and Implementation Plan

Version: 1.3

Date: June 2026

Author: Graham Heap

Status: Baseline

Table Of Contents

1 Introduction	4

1.1 Purpose of the document	4

1.2 Purpose of WIMS	4

1.3 What is WIMS ?	4

1.4 Vision	5

1.5 Purpose	5

1.6 Educational Philosophy	5

1.7 Educational Opportunity	6

2 Summary of  WIMS (Weight Insight Mentoring Service)	7

2.1 Know Thyself	7

2.2 Measure	7

2.3 Learn	8

2.4 Adapt	8

2.5 Project Direction	9

3 Project Framework	10

3.1 Implementation Plan for July 2026 to June 2027	10

3.2 Scope Management	11

3.3 In Scope	11

3.4 Out of Scope	12

3.5 Monthly Planning	13

3.6 Project Reviews	13

3.7 Development Steps	13

3.8 Project Purpose and Business Case	14

3.9 Project Objectives	14

3.10 Project Implementation Plan	14

3.11 Project Milestones	17

3.12 Assumptions	17

3.13 Constraints	17

3.14 High-Level Risks	17

4 Workstreams	18

4.1 Human Biology Research	20

4.2 Overall Philosophy	20

4.3 Development Notes – Human Biology Educational Strategy	21

5 Appendix 1 - WIMS Book Structure	22

5.1 Foundations	22

5.2 Understanding Weight	22

5.3 The WIMS Framework	22

5.4 Practical Application	22

5.5 Real Life	22

5.6 Future Work	22

6 Appendix 3 - Risk Assessment	23

6.1 LinkedIn Profile	23

6.2 Informal SWOT Analysis	23

6.3 Strengths	23

6.3.1 Weaknesses	23

6.3.2 Opportunities	23

6.3.3 Threats	24

6.3.4 Potential Competition	24

6.3.5 Key Reputation Risks	26

6.3.6 Key Validation Questions	26

7 Appendix 5 - Community Engagement	27

7.1 Community Engagement	27

7.2 Community Groups	27

7.2.1 Users	27

7.2.2 Clients	27

7.2.3 Academic Community	27

7.2.4 Human Health Organisations	28

7.2.5 Publishing Partner	28

7.2.6 Community Contributors	28

7.2.7 Community Partners	28

7.3 Community Development Principles	29

8 References	29

9 Glossary	29

Document Revision History

| Document | Revision | Comment | Date |
| --- | --- | --- | --- |
| Initial Service Definition | 1.0 | Draft | June 2026 |
| WIMS - Service Definition and Implementation Plan | 1.0 | Draft | June 2026 |
| WIMS - Service Definition and Implementation Plan | 1.1 | Draft | June 2026 |
| WIMS - Service Definition and Implementation Plan | 1.2 | Draft | July 2026 |
| WIMS - Service Definition and Implementation Plan | 1.3 | Baseline | July 2026 |

# 1 Introduction

## 1.1 Purpose of the document

This document defines the Weight Insight Mentoring Service (WIMS) implementation plan for that service.

The implementation plan covers the period from July 2026 to June 2027 and describes the activities required to establish the service.

An initial Minimum Viable Service (MVS) has been established through the WIMS website (www.ths-wim.com). The website introduces the service, provides educational resources and enables users to enquire about mentoring services.

The service supports two distinct user groups: website users who access the educational resources and clients who engage in mentoring.

## 1.2 Purpose of WIMS

To establish a sustainable WIMS educational platform supporting education, research, mentoring and community engagement, culminating in the publication of the first WIMS book by July 2027.

An initial Minimum Viable Service (MVS) was established through the WIMS website (www.ths-wim.com) in June 2026.

The MVS introduces the concept of a Weight Insight Mentor (WIM) and is based on the June 2026 Fasting Report [Heap, 2026], which introduced the WIMS philosophy: Know Thyself, Measure, Learn and Adapt.

The platform allows users to access the June 2026 Report, and provides a Google Sheet which allows for weight tracking and goal setting. In addition, it allows users to contact the author in the capacity of a Weight Insight Mentor.

This document outlines the strategic development of the service and provides an implementation plan for the next 12 months, with the primary objective of publishing the first WIMS book by July 2027.

## 1.3 What is WIMS ?

The Weight Insight Mentoring Service (WIMS) is an educational platform and mentoring service that helps individuals develop a better understanding of the relationship between lifestyle, human biology and weight management.

Rather than promoting a specific diet or weight-loss programme, WIMS encourages individuals to understand their own bodies through observation, measurement, learning and adaptation.

The service combines educational resources, practical tools, mentoring and ongoing research to support informed decision making. The platform includes reports, articles, presentations, videos, downloadable resources and optional one-to-one mentoring.

WIMS is intended to complement—not replace—the advice provided by qualified medical and healthcare professionals.

## 1.4 Vision

The long-term vision of WIMS is to become a recognised educational platform that improves public understanding of human biology, behaviour and sustainable weight management.

The platform aims to make complex scientific concepts accessible to the general public through clear educational material supported by observation, measurement and evidence-informed learning.

Over time, WIMS will continue to expand through educational publications, online resources, mentoring, community engagement and collaboration with researchers and educational organisations.

The publication of the first WIMS book in July 2027 represents the first major milestone towards achieving this vision.

## 1.5 Purpose

The purpose of WIMS is to help individuals better understand themselves and make informed decisions about their health through education.

The service seeks to improve understanding of the factors influencing weight change by encouraging individuals to observe their own experiences, measure meaningful information, learn from both scientific knowledge and personal observation, and adapt their behaviour accordingly.

The purpose is not simply to help people lose weight, but to develop greater understanding, confidence and long-term autonomy.

## 1.6 Educational Philosophy

The educational philosophy of WIMS is based upon four guiding principles:

Know Thyself

Measure

Learn

Adapt

These principles recognise that every individual is uniquely different and that no single approach is appropriate for everyone.

Rather than prescribing a universal solution, WIMS encourages individuals to develop insight through structured observation, measurement and reflection.

Established scientific knowledge provides important context for understanding human biology; however, personal observation remains central to the learning process. WIMS therefore promotes evidence-informed education that combines current scientific understanding with carefully documented personal experience.

## 1.7 Educational Opportunity

Improving public understanding of human biology, behaviour and sustainable positive weight change represents a significant educational opportunity. WIMS seeks to address this need by providing accessible, evidence-informed educational resources, mentoring and community engagement that support lifelong learning and informed decision-making.

Achieving and maintaining a healthy weight remains one of the largest public health challenges in Ireland and internationally. The increasing prevalence of overweight and obesity, combined with growing public awareness of preventative health, creates a significant opportunity for evidence-informed educational services that support sustainable lifestyle change.

The initial implementation of WIMS will focus on the Dublin region, which provides access to a large and diverse population and opportunities to engage people through online content, mentoring and community-based activities. The service will initially be delivered primarily through a dedicated website, supported by educational publications and digital media.

As the educational platform develops, WIMS has the potential to reach users throughout Ireland and internationally through online delivery. The educational nature of the service means that geographical location is not a significant barrier to participation, allowing future expansion without requiring substantial physical infrastructure.

The implementation strategy therefore begins with the development of a high-quality educational platform and expands services in response to user demand and available resources.

# 2 Summary of  WIMS (Weight Insight Mentoring Service)

## 2.1 Know Thyself

Many people struggle with their weight. The WIMS service aims to help users develop a clearer understanding of where they are now, how they arrived there and what realistic progress looks like.

The content should be written in a relatable, accessible style rather than an academic or technical one.

Users should feel they are learning from someone who has travelled a similar path and spent years studying and experimenting with different approaches.

WIMS aims to help people develop insight, confidence and understanding of how lifestyle influences weight.

The WIMS philosophy is founded on the principle of "Know Thyself".

Every individual is unique. Genetics, biology, life experiences, environment, habits, family influences, and other personal factors all contribute to how each person responds to lifestyle choices.

As scientific understanding develops, additional factors, such as the gut microbiome, may also help explain individual differences.

Rather than assuming that a single approach is suitable for everyone, WIMS encourages individuals to observe themselves, measure meaningful outcomes, learn from their own experiences and adapt their behaviour accordingly.

Human biology and scientific literature provide valuable supporting knowledge that may help explain these observations,  but they do not replace personal observation.

The purpose of WIMS is not to prescribe a universal solution,  but to help individuals develop a better understanding of themselves through evidence-informed observation, measurement, learning and adaptation.

## 2.2 Measure

Measurement remains central to the entire service.

The website (http://www.ths-wim.com) will explain why measurement matters, what should be measured, and how to record data consistently. The weight-tracking spreadsheet will be the primary measuring tool within the WIMS service.

A step-by-step guide will be developed to teach users how to use the spreadsheet effectively and how to interpret the information it provides.

The emphasis is not on reacting to daily fluctuations but on gathering meaningful information over time so that patterns can be identified and understood.

## 2.3 Learn

The website will become an educational platform containing articles, reports, guides, videos, and educational material.

The June Fasting Report is viewed as a foundation document from which many future resources can be developed.

Future content will include both practical and educational topics. Examples include blood sugar, insulin, metabolism, glycogen, fasting, energy balance, weight fluctuations, weekly averages, behaviour change, habit formation, sleep, stress, exercise, and long-term maintenance.

Each article or video will help visitors build their understanding step by step. The aim is to create a coherent body of knowledge rather than a collection of unrelated posts.

YouTube videos will complement the written material by explaining concepts in an accessible way and linking back to the website resources.

Within WIMS, an insight is a meaningful understanding developed through observation, measurement, learning and personal reflection that helps an individual make more informed decisions about their lifestyle and weight.

## 2.4 Adapt

The ultimate goal is to help and support people to make informed choices based on what they learn from the educational platform and from their own weight experiments and experience.

The framework of: Know Thyself, Measure, Learn, and Adapt provides a continuous improvement cycle that can be applied regardless of the specific dietary or lifestyle approach being followed.

The website, videos, spreadsheet, reports, and mentoring services all support this same process.

Over time, users may begin by reading articles and using the spreadsheet, then progress to watching videos, asking questions, and eventually seeking one-to-one client mentoring support.

The mentoring service is viewed as a natural extension of the educational material rather than the primary purpose of the website, however the intention is to present value to the user and good reasons to engage for client paid one on one mentoring. The expectation is that it will be an online service only.

## 2.5 Project Direction

The website will act as the central hub containing educational resources, reports, guides, downloads, videos, and contact information.

The immediate goal is to launch an initial minimal viable service in June 2026 has been achieved.

The longer-term vision includes a growing library of educational content, YouTube channels, mentoring services, and eventually a book based on the accumulated articles, reports, videos, and practical experience.

Weight Insight Mentor Service will develop into an educational platform centred on the principles of:

- Know Thyself

- Measure

- Learn

- Adapt

The website (https://ths-wim.com) will serve as the hub for this educational platform articles, guides, videos, reports, downloads, and mentoring.

The June Fasting Report (2026) demonstrates the application of the tracking spreadsheet and presents real data demonstrating effective weight loss over a period of 6 months.

The spreadsheet is a practical tool.

The videos are the teaching medium.

Mentoring is the personal support layer.

The next section applies, where appropriate and relevant, standard project management techniques

(PMI, 2025) to the implementation of the WIM Service.

# 3 Project Framework

Planning for Action - Action The Plan!

## 3.1 Implementation Plan for July 2026 to June 2027

| Workstream | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Platform Development | X |  |  |  |  |  |  |  |  |  |  |  |
| Human Biology | X |  |  | X |  |  | X |  |  | X |  |  |
| Scientific Literature |  |  |  | X |  |  | X |  |  | X |  |  |
| Theory Development |  |  |  | X |  |  | X |  |  | X |  |  |
| Applied Experiments | X |  |  | X |  |  | X |  |  | X |  |  |
| Community Development |  |  |  | X |  |  | X |  |  | X |  |  |
| Communications | X |  |  | X |  |  | X |  |  | X |  |  |
| Book Development | X |  |  | X |  |  | X |  |  | X |  |  |
| Monthly Programme Review | X | X | X | X | X | X | X | X | X | X | X | X |

Key

Q1 - Jul 26, Aug 26, Sep 26

Q2 - Oct 26, Nov 26, Dec 26

Q3 - Jan 27, Feb 27,  Mar 27

Q4 - Apr 27, May 27, Jun 27

The primary deliverable is the publication of the first WIMS book in July 2027.

The work streams developed during the year should contribute directly or indirectly towards this objective.

The website, software, articles, videos, presentations, research and experiments are not independent projects; they are interconnected workstreams contributing to a single educational platform.

The implementation plan is organised by:

- Time (monthly milestones)
- Workstreams
- Outputs

Each month should produce meaningful outputs across several workstreams.

## 3.2 Scope Management

WIMS initial service will focus on understanding weight change, human biology, and the author's documented observations and educational resources.

Broader topics relating to healthy lifestyles and the wider health effects of fasting are recognised as important areas for future development but remain outside the current programme scope until sufficient evidence, educational content and research have been developed.

A minimal viable service (MVS) website (http://ths-wim.com) exists and was published in June 2026.

The basic one page website introduces the WIMS Service and provides the following resources:

- The June 2026 Fasting Report (Heap, 2026)

- A Google Sheet for tracking, goal settings of the users current weight and allows them to set a weight loss plan for periods in January - December 2026.

The ongoing development of the website to evolve into an educational platform is the initial focus of this document and the expectation is that by September 2026 a stable educational platform will exist which will provide sufficient resources to inform new and current users to be able to apply the basic principles of WIMS to their own situation and will allow for the operational addition of new materials.

This educational platform will essentially consist of technical improvements, articles, videos, presentations, research, experiments, mentoring processes, client journeys, feedback mechanisms, content development, and positioning, all integrated into a single educational platform.

## 3.3 In Scope

The current implementation of WIMS includes:

Development of the WIMS educational platform.

Ongoing improvement of the WIMS website.

Educational articles, reports and presentations.

Development of educational videos.

Weight tracking spreadsheet and associated guidance.

Human Biology educational resources.

Scientific literature reviews.

Working theories and documented observations.

Structured self-observation and personal case studies.

Development of mentoring processes and supporting documentation.

Community engagement and user feedback.

Publication of the first WIMS book.

## 3.4 Out of Scope

The following activities are outside the scope of this implementation plan:

Medical diagnosis or treatment.

Nutritional or dietetic practice.

Clinical research involving participants.

Commercial weight-loss programmes.

Prescription of diets or exercise programmes.

Mobile application development.

International expansion beyond online educational delivery.

Employment of additional staff.

Large-scale software development beyond the current educational platform.

Formal scientific validation studies involving human participants.

## 3.5 Monthly Planning

Each month has clearly defined milestones.

Monthly milestones naturally decompose into weekly missions.

Weekly missions naturally decompose into daily tasks.

Planning, therefore, follows a simple workflow presented in Table (n.1)

| Vision → | WIMS Plan 2026/2027 → | Monthly Milestones → | Weekly Missions → | Daily Tasks Action |
| --- | --- | --- | --- | --- |

Table (n.1) : Planning workflow

The ongoing development of the current website and evolving educational platform should only be released when there is genuine growth. Avoid releasing minor changes simply because they have been completed.

Each release should represent a meaningful improvement that users can appreciate. Development should always be based on features that are known to be deliverable rather than optimistic promises.

## 3.6 Project Reviews

At the end of each month, review:

- What outputs were produced?

- Which workstreams are advanced?

- What was learned?

- Which working theories changed?

- Which growth gates have been reached?

- What are next month's priorities?

## 3.7 Development Steps

Development progresses through capability rather than dates.

Typical gates include:

- Foundation Complete

- Educational Foundation Complete

- Scientific Foundation Complete

- Experimental Readiness

- Publication Readiness

Each step defines the conditions required before the next stage to begin.

## 3.8 Project Purpose and Business Case

In the traditional sense, a detailed business case, market analysis and user base estimate have not been developed for WIMS.

Based on the business opportunity described in Section 1.7, the author believes that sufficient demand exists to support the initial implementation of the service.

## 3.9 Project Objectives

The key project deliverables and milestones are:

- Establish a stable WIMS educational platform by September 2026.

- Establish WIMS - Service Definition and Implementation Plan by July 2027.

- Publish the first WIMS book by July 2027.

Support long-term education, research, mentoring and community engagement.

## 3.10 Project Implementation Plan

| Workstream | Impact | Detail |
| --- | --- | --- |
| Current Implementation | Platform - Spreadsheet improvements. - Improved menu system. - Website navigation. | Content - Convert the June 2026 report into HTML. - Keep the PDF unchanged as the permanent historical record. - Produce the report presentation. - Produce the WIMS presentation. - Produce the "Role of a WI Mentor" presentation. Marketing - Begin YouTube rollout. - Prepare business cards. - Prepare flyers. Community - Community feedback page. - Release Notes page. - Vision and Mission page. |
|  | Historical Documentation | The June 2026 Fasting Report, currently accessible for users by download from the website PDF will remain unchanged. The HTML version becomes an accessible presentation of the same document rather than replacing it. Future reports build on this previous work. |

| Workstream | Impact | Detail |
| --- | --- | --- |
| GitHub Repository | A public GitHub repository should be considered. | Demonstrating software development skills. Demonstrating project management practices. Showing the continuous development of WIMS. Supporting software engineering education. Supporting future collaboration. Providing a professional portfolio. Release Categories Platform Releases Major functional improvements to WIMS. Content Releases Reports. Presentations. Educational resources. Marketing Releases YouTube. Website updates. LinkedIn. Flyers. Business cards. |

3.12 Deliverables

The key deliverables of this project are:

- Educational Platform

- Educational Content

- Mentoring

- Resources

| Educational Platform | WIMS website (Version 1). Educational publications. Presentation materials. Video content. WIM Resource Library. |
| --- | --- |
| Educational Content | June 2026 Fasting Report. Presentation of the June 2026 Fasting Report. YouTube videos based on the presentation. First WIMS book. Book summary after one year of operation. Educational Articles in informal and formal formats and style. |
| Mentoring | Defined mentoring process. Client journey. Personal Profile Mentoring notes. Follow-up |
| Resources | Nutrition - Mediterranean-style eating. - Reducing processed foods. - Increasing vegetables. - Protein strategies. Activity - Walking. - Cycling. - Interval training. - Resistance training. Behaviour - Eating slowly. - Meal planning. - Habit formation. Recovery & Timing - Meal timing. - Intermittent fasting. - Food and drink intake |

## 3.11 Project Milestones

Deliverable  							Milestone

MVS Initial Release of WIMS V1.0  				June 2026

WIMS Service Definition and Implementation Plan 		July 2026

First WIMS Book Publication 				July 2027

## 3.12 Assumptions

The educational platform will be developed incrementally while maintaining a consistent vision for the WIMS service.

The website, educational resources, mentoring and supporting materials can be integrated into a single educational platform.

The publication of the first WIMS book will support the long-term development of the WIMS service.

The required time, human resources and financial resources will be available to complete the planned deliverables.

## 3.13 Constraints

Initial release of WIMS Version 1 completed by the end of June 2026.

A stable educational platform established by September 2026.

Publication of the first WIMS book by July 2027.

All development activities must support the WIMS educational platform and service objectives.

## 3.14 High-Level Risks

A detailed risk assessment will be completed as part of the ongoing project planning and is presented in Appendix 3.

# 4 Workstreams

| Workstream Summary |  |
| --- | --- |
| Educational Platform Development Human Biology Scientific Literature Working Theories Human Biology and Scientific Literature | Practical Experiments Experimental Activity Community Development |

| Work stream | Purpose | Output |
| --- | --- | --- |
| Educational Platform Development | Develop and maintain the WIMS software platform. | Website improvements Reporting User interface Data collection Visualisation GitHub development |
| Human Biology | Develop educational material explaining Human Biology from first principles. | Educational articles Book chapters Website content Presentations Teaching videos |
| Scientific Literature | Develop a comprehensive understanding of current scientific knowledge. | Literature reviews Research summaries Reference library Research Spotlight articles University and researcher profiles |
| Working Theories | Develop conceptual models explaining observed biological behaviour |  |
| Human Biology and Scientific Literature | The Human Biology and Scientific Literature workstreams support the WIMS philosophy by providing additional knowledge that may help explain observed behaviour. They are intended to improve understanding rather than define the purpose of the project. WIMS is not a medical, nutritional or dietetic service. Where appropriate, articles may summarise established scientific knowledge from publicly available and appropriately referenced sources to help explain biological concepts and observations. Such material is clearly distinguished from WIMS observations, working theories and self-experiments. The primary purpose of WIMS remains to encourage individuals to understand themselves through observation, measurement, learning and adaptation. |  |

| Work stream | Purpose | Output |
| --- | --- | --- |
| Practical Experiments | Activities - Record observations - Develop explanations - Compare with published biology - Refine theories | Outputs - Working models - Discussion articles - Future research questions |
| Experimental Activity | Design and conduct structured self-experiments. Initial Focus (2026) Observation only. | Formal experimental design develops after sufficient biological understanding has been established. Outputs - Experimental protocols - Case studies - Data analysis - Research reports |
| Community Development | Develop an active learning community. | Outputs - User feedback - Mentoring - Questions and Answers - Community-inspired improvements |
| Communications | Communicate the WIMS project through education, marketing and customer engagement, making research findings and project outputs accessible to current and future users. | Educational Publications Articles Reports Presentations Educational resources Digital Content Website content Blog posts Videos Social media content Marketing Materials - Business cards - Flyers - Posters - Brochures - Promotional graphics - Produce educational content. - Promote the WIMS service. - Develop marketing materials. - Maintain digital communication channels. - Engage with users and clients. - Get feedback |

| Work stream | Purpose | Output |
| --- | --- | --- |
| Community Engagement | Mentoring support Public talks Workshops Community discussions Client feedback Frequently Asked Questions |  |
| Book Development | Produce the July 2027 publication. | The book develops continuously throughout the project. Articles, presentations, Human Biology lessons, literature reviews and experiments all become future chapters. |

Guiding Principle

One piece of work should generate multiple outputs across educational publications, digital content, marketing materials and community engagement activities.

## 4.1 Human Biology Research

The long-term work will shift from building a stable software platform towards education, Human Biology and evidence-based investigation.

The educational progression becomes:

- Learn and present the basics of human biology.

- Research related scientific literature.

- Develop working theories.

- Design practical experiments.

- Collect evidence.

- Publish observations as carefully documented case studies.

This approach separates established scientific knowledge from personal observations while encouraging continuous learning.

## 4.2 Overall Philosophy

The WIMS programme is not a collection of independent projects.

It is a coordinated educational platform development:

- Every workstream supports the others.

- Every month produces tangible outputs.

- Every output contributes towards the July 2027 book.

The book is therefore not a separate project but the natural culmination of a year's structured learning, software development, research, communication and community engagement.

## 4.3 Development Notes – Human Biology Educational Strategy

As the WIMS platform evolves, the emphasis will increasingly shift from software development towards education, scientific literacy and evidence-based learning.

The long-term objective is not simply to teach fasting, but to help people understand Human Biology.

Educational content will generally follow a structured approach:

- Introduce the relevant Human Biology in clear, accessible language (approximately A-Level to first-year university standard).

- Summarise the current scientific understanding by referencing peer reviewed papers.

- Identifying leading researchers, research groups and universities working in the field.

- Present WIMS observations and self-experiments as clearly identified case studies, distinguishing personal experience from established scientific evidence.

The guiding principle is to help people understand how the human body works through explaining human biology, current scientific evidence and carefully designed, repeatable self-experiments.

# 5 Appendix 1 - WIMS Book Structure

## 5.1 Foundations

Why Another Weight Management Book?

The WIMS Philosophy

Measurement Discipline

The Role of Awareness - Know Thyself

## 5.2 Understanding Weight

Human Biology and Metabolism

Behaviour and Habits

Why Diets may not succeed

## 5.3 The WIMS Framework

Know TheySelf

Measure

Learn

Adapt

## 5.4 Practical Application

Fasting

Feasting

Food and drink

Exercise

## 5.5 Real Life

Case Studies

Lessons Learnt

Long-term Success

## 5.6 Future Work

Ethical Application of AI to the WIMS Service.

# 6 Appendix 3 - Risk Assessment

## 6.1 LinkedIn Profile

Founder & Concept Developer, WIMS (Weight Insight Mentor Service)

Developing WIMS, a resource platform and mentoring service focused on helping people better understand the relationship between lifestyle choices, behaviour, wellbeing, and weight through self-awareness, measurement, learning, and adapting their behaviour based on their own understanding.

The current website represents the initial Minimum Viable Service (MVS), providing access to personal research findings, practical tools, and optional one-to-one mentoring support. The service is being actively developed based on client feedback and ongoing research. Further information is available at www.ths-wims.com.

## 6.2 Informal SWOT Analysis

## 6.3 Strengths

Genuine and authentic personal experience.

Built on observation, measurement, learning, and adaptation.

Resource platform combined with mentoring service.

Non-prescriptive approach.

Encourages self-awareness and informed decision-making.

Practical resources already available (report, spreadsheet, website).

Low-cost Minimum Viable Service already operational.

Human-led rather than technology-led.

Trust-based rather than sales-driven.

Strong alignment between philosophy and development approach.

### 6.3.1 Weaknesses

Service may be difficult to explain quickly.

Visitors may not immediately understand the difference between WIMS and coaching, dieting, or fasting programmes.

Currently based largely on personal experience and observations.

Limited evidence beyond founder experience.

Dependent on Graham's time for mentoring.

The value proposition may not yet be obvious to strangers.

Potential perception that resources could be replaced by free apps or online content.

Website and service offering are still evolving.

### 6.3.2 Opportunities

Friend-to-friend referrals.

Resource sharing within existing social networks.

Growth through trust and recommendations rather than advertising.

Expansion of resources and mentoring offerings.

Development of group mentoring or support options.

Collection of client feedback to improve service.

Building case studies and testimonials over time.

Establishing a niche around weight insight rather than weight-loss programmes.

### 6.3.3 Threats

Being misunderstood as a diet programme.

Being misunderstood as a fasting programme.

Being misunderstood as a coaching business.

Being misunderstood as a medical or nutritional advice service.

Difficulty differentiating from free apps and online resources.

Limited scalability of one-to-one mentoring.

Competitors adopting similar concepts if proven successful.

Public scepticism regarding personal-experience-based approaches.

Lack of clear differentiation could limit referrals.

### 6.3.4 Potential Competition

Weight-Loss Programmes

Commercial slimming organisations.

Structured diet programmes.

Meal-plan-based services.

Likely criticism:

People need structure, not reflection.

People need a programme, not insight.

Dieticians and Nutritionists

Registered nutrition professionals.

Clinical nutrition services.

Likely criticism:

Personal experience is not a professional qualification.

Limited scientific evidence.

Sample size of one.

Doctors and Medical Professionals

GP advice.

Clinical obesity services.

Likely criticism:

Where is the evidence base?

How are medical risks managed?

What safeguards exist for clients with health conditions?

Health Coaches

Lifestyle coaches.

Wellness coaches.

Behaviour-change coaches.

Likely criticism:

We already help people change behaviour.

What is unique about WIMS?

Fasting Communities and Advocates

Online fasting groups.

Fasting coaches.

Likely criticism:

WIMS is not focused enough on fasting.

Fasting should be the primary solution.

Weight-Loss Apps

Tracking apps.

Habit apps.

Calorie counting apps.

Likely criticism:

None directly.

Risk of similar features being incorporated into existing platforms.

Informal Support Networks

Friends.

Family.

Accountability partners.

Peer support groups.

Likely criticism:

Why pay for mentoring when a trusted friend can help?

Counterpoint:

WIMS provides structure, tools, observations, and a mentoring framework that most informal support relationships do not.

### 6.3.5 Key Reputation Risks

Why is a project manager offering a weight-related service?

Being mistaken for a medical professional.

Being mistaken for a nutritionist or dietician.

Being perceived as a fasting evangelist.

Over-promising outcomes.

Being challenged on the evidence base.

Service demand exceeding mentoring capacity.

### 6.3.6 Key Validation Questions

Would I recommend this website to a friend if I had not built it?

Would I feel comfortable giving the business card to someone I care about?

What makes people share the website with others?

What do people think WIMS is after a 30-second visit?

What value does WIMS provide beyond a free app?

What value does WIMS provide beyond a knowledgeable friend?

Can visitors clearly distinguish between the resource platform and the mentoring service?

Does the service solve a real problem that people recognise and value?

# 7 Appendix 5 - Community Engagement

## 7.1 Community Engagement

Community engagement is a continuous workstream within the WIMS Programme rather than a one-time activity. Relationships should develop alongside the maturity of the platform. The objective is to build long-term, mutually beneficial partnerships that strengthen the educational mission of WIMS. Stakeholder engagement should be purposeful, aligned with the values of the programme and appropriate to the current stage of development.

## 7.2 Community Groups

### 7.2.1 Users

Purpose

Develop an active learning community.

Typical Activities

- Gather feedback.

- Improve usability.

- Encourage participation.

- Support continuous improvement.

### 7.2.2 Clients

Purpose

Provide mentoring, consultancy and educational services.

Typical Activities

- Demonstrate the platform.

- Deliver presentations.

- Build long-term client relationships.

### 7.2.3 Academic Community

Purpose

Strengthen the scientific and educational quality of WIMS.

Potential Partners

- Universities.

- Academic departments.

- Individual researchers.

- Research groups.

Typical Activities

- Follow current research.

- Reference published work.

- Engage respectfully with the academic community.

- Identify opportunities for future collaboration.

### 7.2.4 Human Health Organisations

Purpose

Develop relationships with organisations whose objectives align with improving long-term Human

Health.

Potential Activities

- Educational partnerships.

- Public engagement.

- Collaborative initiatives.

- Community outreach.

### 7.2.5 Publishing Partner

The publication of the July 2027 book represents one of the major strategic objectives of the programme.

Rather than approaching publishers only after the manuscript is complete, relationships should be developed progressively throughout the programme.

Activities may include:

- Identifying publishers specialising in Human Biology, health, science and popular science.

- Understanding their publishing philosophy.

- Reviewing submission requirements.

- Studying successful publications.

- Developing a professional book proposal.

- Building a credible educational platform that demonstrates the value of the project.

The objective is to establish a long-term publishing partnership rather than simply seeking publication of a single manuscript.

### 7.2.6 Community Contributors

Purpose: Encourage users to contribute ideas that improve the platform.

Contributions may include:

- Feature suggestions.

- Educational topics.

- Research questions.

- User feedback.

Appropriate recognition should be provided where contributors wish to be acknowledged.

### 7.2.7 Community Partners

As the work matures, additional community groups may include:

- Investors.

- Sponsors.

- Educational charities.

- Professional organisations.

- International collaborators.

These relationships should only be pursued where they support the long-term educational vision of WIMS.

## 7.3 Community Development Principles

- Build relationships gradually.

- Focus on long-term trust rather than short-term opportunities.

- Seek partnerships that align with the educational mission.

- Ensure relationships provide value to both WIMS and the stakeholder.

- Allow stakeholder engagement to grow naturally as the programme matures.

Community development should therefore be viewed as a long-term action of relationship building that supports the continued development, credibility and impact of WIMS.

# 8 References

Heap, G. (2026). June 2026 fasting report: Weight management as measurement and a feedback system: A reflective, data-led personal case study (September 2025–January 2026).

Project Management Institute. (2025). A guide to the Project Management Body of Knowledge (PMBOK® Guide) (8th ed.). Project Management Institute.

# 9 Glossary

Adapt

Baseline

Book

Client

Educational Platform

Fasting

Fasting Cycle

Feasting

Insight

Intervention

Know Thyself

Learn

Measurement

Mentoring

Service

Trend

User

Weight Insight

Weight Insight Mentor

Website

Working Definitions

Baseline – The initial reference point against which future progress or change is measured.

Insight – A meaningful understanding developed through measurement, learning and adaptation.

Weight Insight Mentor – A mentor who helps individuals better understand their own weight-change journey through education and evidence-informed guidance.