## Project Status
Milestone | Planned Target
Inital MVS Release | 2026-06-01
Baseline Implementaiton Plan | 2026-07-01
Stable WIMS Platform | September 206

## Key Deliverables - Milestones
| PD | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4
Deliverables |  | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-02 | 2026-11-02 | 2026-12-03 | 2027-01-03 | 2027-02-03 | 2027-03-06 | 2027-04-06 | 2027-05-07 | 2027-06-07
WIMS SD & I Plan | bar: 2026-07-01
Work Streams
1.0 WIMS Book | WBK | 2027-06-07: Due
2.0 WIMS Educational Platform | WEP | 2026-07-01: R1.1; 2026-08-01: R1.2; 2026-09-01: R.3
3.0 WIMS Educational Content | WEC | 2026-08-01: WBS; 2026-09-01: WBS
4.0 WIMS Practical Theory | WPT
5.0 WIMS Community Engagement | WCE
6.0 WIMS Communications | WCM

## Key Deliverables - Milestones -
|  | PD | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4
| Deliverables |  | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-02 | 2026-11-02 | 2026-12-03 | 2027-01-03 | 2027-02-03 | 2027-03-06 | 2027-04-06 | 2027-05-07 | 2027-06-07 | Totals
PM |  |  | PM01 | PM02 | PM03 | PM04 | PM05 | PM06 | PM07 | PM08 | PM09 | PM10 | PM11 | PM12
PW |  |  | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 52
PD |  |  | 20 | 25 | 20 | 20 | 25 | 20 | 20 | 20 | 25 | 20 | 25 | 20 | 260
| WIMS SD & I Plan |  | PM01: 0
Work Streams
| 0.0 WIMS Planning | PLN | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 5 | 5 | 4 | 53
| 1.0 WIMS Book | WBK |  | 0.75 | 0.75 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 40.5
| 2.0 WIMS Educational Platform | WEP | 12 | 15.75 | 12.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 49
| 3.0 WIMS Educational Content | WEC | 4 | 0.75 | 0.75 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 1 | 41.5
| 4.0 WIMS Practical Theory | WPT |  | 0.75 | 0.75 | 2 | 2.5 | 2 | 2 | 2 | 2.5 | 2 | 2.5 | 2 | 21
| 5.0 WIMS Community Engagement | WCE |  | 0.75 | 0.75 | 2 | 2.5 | 2 | 2 | 2 | 2.5 | 2 | 2.5 | 2 | 21
| 6.0 WIMS Communications | WCM |  | 0.75 | 0.75 | 2 | 2.5 | 2 | 2 | 2 | 2.5 | 2 | 2.5 | 2 | 21
Totals |  |  | 20 | 24.5 | 20 | 19 | 23.5 | 19 | 19 | 19 | 23.5 | 20 | 23.5 | 16 | 247 | 247
Unallocated |  |  | 0 | 0.5 | 0 | 1 | 1.5 | 1 | 1 | 1 | 1.5 | 0 | 1.5 | 4 | 13 | 13
Formulas:
Q1 = [Q1]+31

## Project Key
Key | Project Name | PD | Work Streams | WC | Component Deliverables | CD | Project Action | PN
Project | Project Office | PO | WIMS Book | WBK |  |  | Plan | PLN
| Project Control | PC | WIMS Education Platform | WEP |  |  | Work Break Down Structure | WBS
[5 empty] | Human Bioliogy Basics | HBB
| Project Year | PY |  |  | Human Bioliogy Research | HBR
| Project Month | PM | WIMS Education Content | WEC
| Project Week | PW | WIMS Practical Theory | WPT
|  |  | WIMS Community Engagement | WCE
| Project Status | PS | WIMS Communication | WCM
Project RAIDD | Project Risk | PR
| Project Assumptions | PA
| Project Issue | PI
| Project Definition | PD
| Project Dependency | PY
| Project Decisions | PS
| Project Park | PP
| Project Code | PE

## Project Components
Articles
Reports
Presentations
Website Content
Review
Reference Library
Website Releases
YouTube Content
Social Media
Marketing Materials
Book structure
Draft Chapters
Review Versions
Publication

## Project Weeks (0)
Project Quarter | Project Month | Project Week # | Start | End
PQ1 | PM01 | PW01 | 2026-07-06 | 2026-07-10
|  | PW02 | 2026-07-13 | 2026-07-17
|  | PW03 | 2026-07-20 | 2026-07-24
|  | PW04 | 2026-07-27 | 2026-07-31
PQ1 | PM02 | PW05 | 2026-08-03 | 2026-08-07
|  | PW06 | 2026-08-10 | 2026-08-14
|  | PW07 | 2026-08-17 | 2026-08-21
|  | PW08 | 2026-08-24 | 2026-08-28
|  | PW09 | 2026-08-31 | 2026-09-04
PQ1 | PM03 | PW10 | 2026-09-07 | 2026-09-11
|  | PW11 | 2026-09-14 | 2026-09-18
|  | PW12 | 2026-09-21 | 2026-09-25
|  | PW13 | 2026-09-28 | 2026-10-02
PQ2 | PM04 | PW14 | 2026-10-05 | 2026-10-09
|  | PW15 | 2026-10-12 | 2026-10-16
|  | PW16 | 2026-10-19 | 2026-10-23
|  | PW17 | 2026-10-26 | 2026-10-30
PQ2 | PM05 | PW18 | 2026-11-02 | 2026-11-06
|  | PW19 | 2026-11-09 | 2026-11-13
|  | PW20 | 2026-11-16 | 2026-11-20
|  | PW21 | 2026-11-23 | 2026-11-27
|  | PW22 | 2026-11-30 | 2026-12-04
PQ3 | PM06 | PW23 | 2026-12-07 | 2026-12-11
|  | PW24 | 2026-12-14 | 2026-12-18
|  | PW25 | 2026-12-21 | 2026-12-25
|  | PW26 | 2026-12-28 | 2027-01-01
PQ3 | PM07 | PW27 | 2027-01-04 | 2027-01-08
|  | PW28 | 2027-01-11 | 2027-01-15
|  | PW29 | 2027-01-18 | 2027-01-22
|  | PW30 | 2027-01-25 | 2027-01-29
PQ3 | PM08 | PW31 | 2027-02-01 | 2027-02-05
|  | PW32 | 2027-02-08 | 2027-02-12
|  | PW33 | 2027-02-15 | 2027-02-19
|  | PW34 | 2027-02-22 | 2027-02-26
PQ3 | PM09 | PW35 | 2027-03-01 | 2027-03-05
|  | PW36 | 2027-03-08 | 2027-03-12
|  | PW37 | 2027-03-15 | 2027-03-19
|  | PW38 | 2027-03-22 | 2027-03-26
|  | PW39 | 2027-03-29 | 2027-04-02
PQ4 | PM10 | PW40 | 2027-04-05 | 2027-04-09
|  | PW41 | 2027-04-12 | 2027-04-16
|  | PW42 | 2027-04-19 | 2027-04-23
|  | PW43 | 2027-04-26 | 2027-04-30
PQ4 | PM11 | PW44 | 2027-05-03 | 2027-05-07
|  | PW45 | 2027-05-10 | 2027-05-14
|  | PW46 | 2027-05-17 | 2027-05-21
|  | PW47 | 2027-05-24 | 2027-05-28
|  | PW48 | 2027-05-31 | 2027-06-04
PQ4 | PM12 | PW49 | 2027-06-07 | 2027-06-11
|  | PW50 | 2027-06-14 | 2027-06-18
|  | PW51 | 2027-06-21 | 2027-06-25
|  | PW52 | 2027-06-28 | 2027-07-02
Formulas:
End = [Start]+5-1
End = [End, row above]+7
Start = [Start, row above]+7

## Project Weeks(R)
Calandar Month | Project Quarter | Project Month | Project Week | Start | End | Calandar Month | Project Quarter | Project Month | Project Week | Start | End
July | PQ1 | PM01 | PW01 | 2026-07-06 | 2026-07-10 | January | PQ3 | PM07 | PW27 | 2027-01-04 | 2027-01-08
|  |  | PW02 | 2026-07-13 | 2026-07-17 |  |  |  | PW28 | 2027-01-11 | 2027-01-15
|  |  | PW03 | 2026-07-20 | 2026-07-24 |  |  |  | PW29 | 2027-01-18 | 2027-01-22
|  |  | PW04 | 2026-07-27 | 2026-07-31 |  |  |  | PW30 | 2027-01-25 | 2027-01-29
August | PQ1 | PM02 | PW05 | 2026-08-03 | 2026-08-07 | February | PQ3 | PM08 | PW31 | 2027-02-01 | 2027-02-05
|  |  | PW06 | 2026-08-10 | 2026-08-14 |  |  |  | PW32 | 2027-02-08 | 2027-02-12
|  |  | PW07 | 2026-08-17 | 2026-08-21 |  |  |  | PW33 | 2027-02-15 | 2027-02-19
|  |  | PW08 | 2026-08-24 | 2026-08-28 |  |  |  | PW34 | 2027-02-22 | 2027-02-26
|  |  | PW09 | 2026-08-31 | 2026-09-04
September | PQ1 | PM03 | PW10 | 2026-09-07 | 2026-09-11 | March | PQ3 | PM09 | PW35 | 2027-03-01 | 2027-03-05
|  |  | PW11 | 2026-09-14 | 2026-09-18 |  |  |  | PW36 | 2027-03-08 | 2027-03-12
|  |  | PW12 | 2026-09-21 | 2026-09-25 |  |  |  | PW37 | 2027-03-15 | 2027-03-19
|  |  | PW13 | 2026-09-28 | 2026-10-02 |  |  |  | PW38 | 2027-03-22 | 2027-03-26
[9 empty] | PW39 | 2027-03-29 | 2027-04-02
October | PQ2 | PM04 | PW14 | 2026-10-05 | 2026-10-09 | April | PQ4 | PM10 | PW40 | 2027-04-05 | 2027-04-09
|  |  | PW15 | 2026-10-12 | 2026-10-16 |  |  |  | PW41 | 2027-04-12 | 2027-04-16
|  |  | PW16 | 2026-10-19 | 2026-10-23 |  |  |  | PW42 | 2027-04-19 | 2027-04-23
|  |  | PW17 | 2026-10-26 | 2026-10-30 |  |  |  | PW43 | 2027-04-26 | 2027-04-30
November | PQ2 | PM05 | PW18 | 2026-11-02 | 2026-11-06 | May | PQ4 | PM11 | PW44 | 2027-05-03 | 2027-05-07
|  |  | PW19 | 2026-11-09 | 2026-11-13 |  |  |  | PW45 | 2027-05-10 | 2027-05-14
|  |  | PW20 | 2026-11-16 | 2026-11-20 |  |  |  | PW46 | 2027-05-17 | 2027-05-21
|  |  | PW21 | 2026-11-23 | 2026-11-27 |  |  |  | PW47 | 2027-05-24 | 2027-05-28
|  |  | PW22 | 2026-11-30 | 2026-12-04 |  |  |  | PW48 | 2027-05-31 | 2027-06-04
December | PQ3 | PM06 | PW23 | 2026-12-07 | 2026-12-11 | June | PQ4 | PM12 | PW49 | 2027-06-07 | 2027-06-11
|  |  | PW24 | 2026-12-14 | 2026-12-18 |  |  |  | PW50 | 2027-06-14 | 2027-06-18
|  |  | PW25 | 2026-12-21 | 2026-12-25 |  |  |  | PW51 | 2027-06-21 | 2027-06-25
|  |  | PW26 | 2026-12-28 | 2027-01-01 |  |  |  | PW52 | 2027-06-28 | 2027-07-02

## Project Calendar
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
PM01 | PM02 | PM03 | PM04 | PM05 | PM06 | PM07 | PM08 | PM09 | PM10 | PM11 | PM12 | Project Weeks
PW01 | PW05 | PW10 | PW14 | PW18 | PW23 | PW27 | PW31 | PW35 | PW40 | PW44 | PW49
PW02 | PW06 | PW11 | PW15 | PW19 | PW24 | PW28 | PW32 | PW36 | PW41 | PW45 | PW50
PW03 | PW07 | PW12 | PW16 | PW20 | PW25 | PW29 | PW33 | PW37 | PW42 | PW46 | PW51
PW04 | PW08 | PW13 | PW17 | PW21 | PW26 | PW30 | PW34 | PW38 | PW43 | PW47 | PW52
| PW09 |  |  | PW22 |  |  |  | PW39 |  | PW48
4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 4 | 52
4 | 9 | 13 | 17 | 22 | 26 | 30 | 34 | 39 | 43 | 48 | 52 | 0 | Cross Check

## Project Weeks (1)
Project Quarter | Calandar Month | Project Month | [6 empty] | Project Quarter | Calandar Month | Project Month
PQ1 | July | PM01 | Project Week | PW01 | PW02 | PW03 | PW04 |  | PQ3 | January | PM07 | Week | PW27 | PW28 | PW29 | PW30
|  |  | Start | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 |  |  |  |  | Start | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
|  |  | End | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 |  |  |  |  | End | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29
| August | PM02 | Week | PW05 | PW06 | PW07 | PW08 | PW09 |  | February | PM08 | Week | PW31 | PW32 | PW33 | PW34
|  |  | Start | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 |  |  |  | Start | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22
|  |  | End | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 |  |  |  | End | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26
| September | PM03 | Week | PW10 | PW11 | PW12 | PW13 |  |  | March | PM09 | Week | PW35 | PW36 | PW37 | PW38 | PW39
|  |  | Start | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 |  |  |  |  | Start | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
|  |  | End | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 |  |  |  |  | End | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02
PQ2 | October | PM04 | Week | PW14 | PW15 | PW16 | PW17 |  | PQ4 | April | PM10 | Week | PW40 | PW41 | PW42 | PW43
|  |  | Start | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 |  |  |  |  | Start | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26
|  |  | End | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 |  |  |  |  | End | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30
| November | PM05 | Week | PW18 | PW19 | PW20 | PW21 | PW22 |  | May | PM10 | Week | PW44 | PW45 | PW46 | PW47 | PW48
|  |  | Start | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 |  |  |  | Start | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31
|  |  | End | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 |  |  |  | End | 2027-05-07 | 2027-05-14 | 2027-05-21 | 2027-05-28 | 2027-06-04
| December | PM06 | Week | PW23 | PW24 | PW25 | PW26 |  |  | June | PM10 | Week | PW49 | PW50 | PW51 | PW52
|  |  | Start | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 |  |  |  |  | Start | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28
|  |  | End | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 |  |  |  |  | End | 2027-06-11 | 2027-06-18 | 2027-06-25 | 2027-07-02