## Project Timesheet
Calandar Month | Project Quarter | Project Month | Project Week | Start | End | Calandar Month | Project Quarter | Project Month | Project Week | Start | End
July | PQ1 | PM01 | PW01 | 2026-07-06 | 2026-07-10 | January | PQ3 | PM07 | PW27 | 2027-01-04 | 2027-01-08
|  | PM01 | PW02 | 2026-07-13 | 2026-07-17 |  |  |  | PW28 | 2027-01-11 | 2027-01-15
|  | PM01 | PW03 | 2026-07-20 | 2026-07-24 |  |  |  | PW29 | 2027-01-18 | 2027-01-22
|  | PM01 | PW04 | 2026-07-27 | 2026-07-31 |  |  |  | PW30 | 2027-01-25 | 2027-01-29
August | PQ1 | PM02 | PW05 | 2026-08-03 | 2026-08-07 | February | PQ3 | PM08 | PW31 | 2027-02-01 | 2027-02-05
|  |  | PW06 | 2026-08-10 | 2026-08-14 |  |  |  | PW32 | 2027-02-08 | 2027-02-12
|  |  | PW07 | 2026-08-17 | 2026-08-21 |  |  |  | PW33 | 2027-02-15 | 2027-02-19
|  |  | PW08 | 2026-08-24 | 2026-08-28 |  |  |  | PW34 | 2027-02-22 | 2027-02-26
|  |  | PW09 | 2026-08-31 | 2026-09-04
September | PQ1 | PM03 | PW10 | 2026-09-07 | 2026-09-11 | March | PQ3 | PM09 | PW35 | 2027-03-01 | 2027-03-05
|  |  | PW11 | 2026-09-14 | 2026-09-18 |  |  |  | PW36 | 2027-03-08 | 2027-03-12
|  |  | PW12 | 2026-09-21 | 2026-09-25 |  |  |  | PW37 | 2027-03-15 | 2027-03-19
|  |  | PW13 | 2026-09-28 | 2026-10-02 |  |  |  | PW38 | 2027-03-22 | 2027-03-26
[9 empty] | PW39 | 2027-03-29 | 2027-04-02
October | PQ2 | PM04 | PW14 | 2026-10-05 | 2026-10-09 | April | PQ4 | PM10 | PW40 | 2027-04-05 | 2027-04-09
|  |  | PW15 | 2026-10-12 | 2026-10-16 |  |  |  | PW41 | 2027-04-12 | 2027-04-16
|  |  | PW16 | 2026-10-19 | 2026-10-23 |  |  |  | PW42 | 2027-04-19 | 2027-04-23
|  |  | PW17 | 2026-10-26 | 2026-10-30 |  |  |  | PW43 | 2027-04-26 | 2027-04-30
November | PQ2 | PM05 | PW18 | 2026-11-02 | 2026-11-06 | May | PQ4 | PM11 | PW44 | 2027-05-03 | 2027-05-07
|  |  | PW19 | 2026-11-09 | 2026-11-13 |  |  |  | PW45 | 2027-05-10 | 2027-05-14
|  |  | PW20 | 2026-11-16 | 2026-11-20 |  |  |  | PW46 | 2027-05-17 | 2027-05-21
|  |  | PW21 | 2026-11-23 | 2026-11-27 |  |  |  | PW47 | 2027-05-24 | 2027-05-28
|  |  | PW22 | 2026-11-30 | 2026-12-04 |  |  |  | PW48 | 2027-05-31 | 2027-06-04
December | PQ3 | PM06 | PW23 | 2026-12-07 | 2026-12-11 | June | PQ4 | PM12 | PW49 | 2027-06-07 | 2027-06-11
|  |  | PW24 | 2026-12-14 | 2026-12-18 |  |  |  | PW50 | 2027-06-14 | 2027-06-18
|  |  | PW25 | 2026-12-21 | 2026-12-25 |  |  |  | PW51 | 2027-06-21 | 2027-06-25
|  |  | PW26 | 2026-12-28 | 2027-01-01 |  |  |  | PW52 | 2027-06-28 | 2027-07-02

## July Planned Activity
|  | Weekly Timesheets |  | M | T | W | T | F | Total
July | PQ1 | PM01 | PW01 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10
Establish PO
|  | WIMS Architecture Definition |  | 4 | 4 | 4 | 4 | 4 | 20
|  | Review Baseline Documentation |  | 4 | 4 | 4 | 4 | 4 | 20
|  |  |  | 8 | 8 | 8 | 8 | 8 | 40
|  | Weekly Timesheets |  | M | T | W | T | F | Total
July | PQ1 | PM01 | PW02 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17
Project Governamce
|  | Review Directory Structure |  | 4 | 4 | 4 | 4 | 4 | 20
|  | Review Baseline Documentation |  | 4 | 4 | 4 | 4 | 4 | 20
|  |  |  | 8 | 8 | 8 | 8 | 8 | 40
July | PQ1 | Weekly Timesheets |  | M | T | W | T | F | Total
|  | PM01 | PW03 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24
|  | Establish PO |  | 4 | 4 | 4 | 4 | 4 | 20
|  | Review Baseline Documentation |  | 4 | 4 | 4 | 4 | 4 | 20
|  |  |  | 8 | 8 | 8 | 8 | 8 | 40
July | PQ1 | Weekly Timesheets |  | M | T | W | T | F | Total
|  | PM01 | PW04 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31
|  | Establish PO |  | 4 | 4 | 4 | 4 | 4 | 20
|  | Review Baseline Documentation |  | 4 | 4 | 4 | 4 | 4 | 20
|  |  |  | 8 | 8 | 8 | 8 | 8 | 40
Formulas:
T = [M]+1

## July Actuals
|  | Weekly Timesheets |  | M | T | W | T | F | Total
July | PQ1 | PM01 | PW01 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10
Establish PO
|  | WIMS Architecture Definition |  | 4 | 4 | 4 | 4 | 4 | 20
|  | Review Baseline Documentation |  | 4 | 4 | 4 | 4 | 4 | 20
|  |  |  | 8 | 8 | 8 | 8 | 8 | 40
|  | Weekly Timesheets |  | M | T | W | T | F | Total
July | PQ1 | PM01 | PW02 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17
Project Governamce
|  | Review Directory Structure |  | 4 | 4 | 4 | 4 | 4 | 20
|  | Review Baseline Documentation |  | 4 | 4 | 4 | 4 | 4 | 20
|  |  |  | 8 | 8 | 8 | 8 | 8 | 40
July | PQ1 | Weekly Timesheets |  | M | T | W | T | F | Total
|  | PM01 | PW03 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24
|  | Establish PO |  | 4 | 4 | 4 | 4 | 4 | 20
|  | Review Baseline Documentation |  | 4 | 4 | 4 | 4 | 4 | 20
|  |  |  | 8 | 8 | 8 | 8 | 8 | 40
July | PQ1 | Weekly Timesheets |  | M | T | W | T | F | Total
|  | PM01 | PW04 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31
|  | Establish PO |  | 4 | 4 | 4 | 4 | 4 | 20
|  | Review Baseline Documentation |  | 4 | 4 | 4 | 4 | 4 | 20
|  |  |  | 8 | 8 | 8 | 8 | 8 | 40
Formulas:
T = [M]+1

## Planned Work PW03
July | PQ1 | Planned Work | ETC |  | M | T | W | T | F | Actuals
|  | PM01 |  | PW03 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24
|  | PO – Project Office | 8 |  | 2 |  |  |  | 4 | 6
|  | Complete Project Office Documentation | [7 empty] | 0
|  | PC - Project Control | 8 | [6 empty] | 0
|  | Configuration Management | [7 empty] | 0
|  | Baseline Management | [7 empty] | 0
|  | Implementation Planning | [7 empty] | 0
|  | WEP – WIMS Education Platform | 16 |  | 4 | 4 | 8 | 12 |  | 28
|  | HTML June Fasting Report |  |  | 2 |  |  |  |  | 2
|  | Introductory Educational Pages | [7 empty] | 0
|  | WCM – WIMS Communications | 4 | [6 empty] | 0
|  | YouTube educational content |  |  |  | 4 |  |  |  | 4
|  | Presentation material | [7 empty] | 0
|  | PM – Planning & Reporting | 4 | [6 empty] | 0
|  | Weekly Reporting | [7 empty] | 0
|  | PM02 preparation | [7 empty] | 0
|  | PW04 planning | [7 empty] | 0
|  | Totals | 40 | 0 | 8 | 8 | 8 | 12 | 4 | 40
Formulas:
T = [M]+1

## Planned Work PW04
July | PQ1 | Planned Work |  |  |  | M | T | W | T | F | Actuals | Cross Check
|  | PM01 |  | ETC | PW04 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31
|  | PO – Project Office | 5 | [8 empty] | 5
|  | Identify and list Docmentation to review |  | 1 |  |  |  |  | 1 |  | 1
|  | Review Documentation |  | 4 |  |  |  |  | 4 |  | 4
|  | PC - Project Control | 8 | [7 empty] | 0 | 6
|  | Project Reporting and Planning PW04 |  | 8 |  | 2 |  |  |  | 4 | 6
|  | WEP – WIMS Education Platform | 19 | [7 empty] | 0 | 8
|  | Review live Test for release V1.1 |  | 4 |  | 2 | 2 |  |  |  | 4
|  | Code Review |  | 4 |  | 2 | 2 |  |  |  | 4
|  | Update Standards |  | 4 |  | 1 | 1 | 2 |  |  | 4
|  | Prepare for release V1.1 |  | 4 |  | 1 | 1 | 1 | 1 |  | 4
|  | Testing |  | 2 |  |  |  | 2 |  |  | 2
|  | Decision to Release |  | 1 | [5 empty] | 1 | 1
|  | WCM - WIMS Communications | 2 | [7 empty] | 0 | 2
|  | Prepare Release Statement |  | 2 | [5 empty] | 2 | 2
|  | Totals | 34 | 32 | 0 | 8 | 6 | 5 | 6 | 5 | 30 | 30
|  | Float | 6 | 8 | 8 | 0 | 2 | 3 | 2 | 3 | 10 | 10