## WIMS - Project Planning Discussion (Q1 Planning )

### Planning Approach

For each task:

- Action Now (Q1)

- Future Workstream (Q2, Q3 or Q4)

This allows all ideas to be captured while only committing to work appropriate for the current quarter.

The planning hierarchy is:

Project
→ Workstream
→ Task
→ Action Now or Future Workstream

### Current Q1 Tasks

#### Platform Development

- Convert June report to HTML.

- Continue development of Website V2.0 for release at the end of July.

- Develop the content publishing system.

- Design article and blog templates.

- Implement a content management mechanism.

- Implement categories and search.

- Standardise the development environment.

- Introduce a testing process.

- Develop the software release process.

- Produce the Weight Tracker user guide.

#### Communications

- Produce the June presentation.

- Launch the WIMS YouTube channel.

- Publish the June report.

- Develop the marketing strategy.

- Define local and online engagement.

- Assess the use of social media.

- Produce four posts for August.

#### Book Development

- Complete the WIMS Definition document.

- Complete the Service Definition.

- Complete the Vision.

- Complete the implementation plan.

- Complete the SWOT analysis.

- Produce the book structure.

- Draft the Introduction.

- Draft the Conclusions.

#### Human Biology

- Produce the Human Biology of Digestion paper.

- Maintain approximately UK A-Level standard.

- Produce the first Human Biology article.

#### Monthly Review

- Review Q1 progress.

- Identify preparation tasks for Q2.

### Planned Platform Releases

End of July

- Website Version 2.0

End of August

- Website Version 2.1

End of September

- Major platform release.

October onwards

- Maintenance releases.

- Ongoing publication of articles, blogs and educational material.

### Platform Objective

The website should become a publishing platform rather than a static website.

It should support:

- Publishing articles.

- Publishing blogs.

- Organising content by category.

- Searching content.

- Maintaining version control.

- Testing before release.

- Publishing regular educational content with minimal effort.

### Overall Objective

Complete the core platform during Q1 so that from October onwards the primary effort shifts from software development to producing and publishing educational content that supports the WIMS project and the publication of the first WIMS book in July 2027.

I think you've reached the next level of planning.

So far you've identified what needs to be done (the workstreams and tasks). Now you're asking:

- What should be done first?

- What depends on something else?

- What is urgent?

- What provides the greatest value?

- What can run in parallel?

That's classic project scheduling.

I wouldn't start by assigning dates. I'd do this in three passes.

## Step 1 - Prioritise For every task assign one of four priorities. Priority; Meaning. P1; Critical - must be completed first or blocks other work.. P2; Important - should be completed this month.. P3; Desirable - complete if time permits.. P4; Future - can wait until August or later..

## Step 2 - Identify Dependencies

Example:

Complete WIMS Definition

↓

Website content

↓

Presentation

↓

YouTube launch

Another example

Standardise development environment

↓

Testing process

↓

Release process

↓

Website V2.0

The dependency diagram almost creates the schedule for you.

## Step 3 - Build Weekly Iterations

Rather than saying

Week 1
Week 2
Week 3

I'd give each week an objective.

### Week 1

Planning and Foundations

Deliverables

- Complete WIMS Definition

- Complete implementation plan

- Complete SWOT

- Standardise development environment

- Define testing process

- Define release process

### Week 2

Platform

Deliverables

- Convert June report to HTML

- Website V2.0 development

- Article templates

- Blog templates

- Content publishing system

### Week 3

Content

Deliverables

- Presentation

- Digestion paper

- Weight Tracker guide

- Human Biology article

- Book structure

### Week 4

Release

Deliverables

- Release Website V2.0

- Launch YouTube channel

- Publish report

- Publish presentation

- Review July

- Plan August

## Critical Path

If I were identifying the critical path, it would probably be:

Planning

↓

WIMS Definition

↓

Website V2.0

↓

Publishing System

↓

Release

↓

Communications

Everything else can move around those milestones.

I also think you should estimate each task.

| Task | Estimate |
| --- | --- |
| Convert report to HTML | 6 hrs |
| Website V2.0 | 35 hrs |
| WIMS Definition | 8 hrs |
| Digestion paper | 12 hrs |
| Presentation | 5 hrs |
| YouTube setup | 4 hrs |
| Testing process | 4 hrs |
| Release process | 3 hrs |

Once you estimate the work, you can see whether July contains 80 hours of work or 200 hours. That gives you an evidence-based way to decide whether something should move to August, rather than relying on intuition.

I think this is where your project management background will really help. You're no longer creating a list of tasks—you are developing a realistic execution plan with priorities, dependencies, estimates, and weekly deliverables. That's much closer to how a professional implementation schedule is built.

😂 I smiled at the last line because I think you've identified the real project risk.

"I am liable to do all of it."

That's probably the biggest risk to the July plan—not lack of motivation, but too much motivation.

I think there are actually three categories, not two.

| Category | Question | Action |
| --- | --- | --- |
| Must Do in July | Does other work depend on this? | Complete in July. |
| Should Do in July | Would it be beneficial if time allows? | Start or complete if capacity exists. |
| Can Wait | Does nothing depend on it yet? | Schedule for August or September. |

For example:

### Must Do in July

- Complete the WIMS Definition.

- Complete the implementation plan.

- Standardise the development environment.

- Introduce the testing process.

- Develop Website V2.0.

- Convert the June report to HTML.

- Define the release process.

- Build the content publishing mechanism.

- Produce the July release.

Without these, August becomes difficult.

### Should Do in July

- Launch the YouTube channel.

- Produce the presentation.

- Weight Tracker paper.

- Book structure.

- Marketing strategy.

- Social media assessment.

Useful, but they don't block the platform.

### Can Wait Until August/September

- Human Biology of Digestion paper.

- First Human Biology article.

- Four August social media posts (they only need to be ready before August).

- Local outreach.

- Expanded marketing materials.

- Book Introduction.

- Book Conclusions.

These all depend on the platform existing first.

I think there's a useful principle emerging:

Build the factory before trying to maximise production.

In July you're building the factory:

- the website,

- the publishing workflow,

- the testing process,

- the release process,

- the development environment.

From August onwards, you start using that factory to produce:

- articles,

- videos,

- book chapters,

- presentations,

- marketing material.

That's a much more sustainable way to think about it.

And knowing you, I'd suggest one personal rule for July:

Before starting a new task, ask: "Does this help me deliver the July release?"

If the answer is no, capture it for August or September and carry on with the current task. That simple question will probably save you from trying to do everything at once while still ensuring none of your ideas are lost.

Thank you, Graham. I actually think we've found the planning model that fits the way you naturally work.

At the beginning of our discussion we were talking about workstreams. Now we've added the missing layer: execution.

So the planning hierarchy becomes:

Annual Project (July 2026 – June 2027)

↓

Quarterly Workstreams

↓

Monthly Planning

↓

Must Do

Should Do

Can Wait

↓

Weekly Plan

↓

Daily Actions

That gives you a clear decision process:

- Does this belong in the project?

- Which workstream does it belong to?

- Which quarter?

- Does it need to be done this month?

- Is it a Must Do, Should Do, or Can Wait?

- Which week will it be completed?

- What is today's action?

The key insight from today, though, wasn't the structure—it was the question you asked yourself:

"What can wait until August and September, and what needs to be done in July?"

That's exactly how a project manager protects a schedule. Instead of asking, "Can I do this?", you're asking, "Does this need to be done now?"

I also think you've identified July's theme:

Build the platform.

August becomes:

Use the platform.

September becomes:

Complete and stabilise the platform.

October onwards becomes:

Maintain the platform and publish educational content.

That's a very natural lifecycle.

I have a feeling that once you've worked through July using this approach, the monthly planning for August and September will become much easier because you'll already have a repeatable process for deciding what gets done now and what waits. That's a solid foundation for the rest of the WIMS project.

I completely agree, and that's an important planning principle to make explicit.

At the moment, almost all of your work is building capability. Once you have users or clients, part of your work changes from building to delivering.

Your priorities naturally become:

- Existing users and clients (service delivery)

- Committed releases (what you've promised publicly)

- Platform development

- Research and content development

- Future ideas and enhancements

In project management terms, users and clients become operational work. If someone has paid for your service or is actively using it, responding to them takes precedence because that's where the value is being delivered.

That doesn't mean development stops—it means it has to be planned around service delivery.

I can also see your year evolving in phases:

- July–September: Build the platform and establish the processes.

- October onwards: Balance platform maintenance with supporting users, publishing content, and refining WIMS based on real-world feedback.

One thing I'd add to your planning document is a simple rule such as:

Priority Rule: Active users and clients take precedence over planned development work. Project tasks should be rescheduled where necessary to maintain the quality and continuity of service delivery.

That gives you a clear decision-making principle. If you ever find yourself wondering whether to finish a new feature or help a client, the framework already provides the answer.

I think those are both good additions, and they fit naturally into the July planning.

### New Q1 Action Items

Community Development

- Produce user and client engagement materials.

  - Flyer

  - Handout

  - Poster (TBD)

This creates the assets you'll need before actively approaching potential users.

Monthly Review / Planning

- Complete the SWOT analysis.

- Identify mitigation actions for each significant risk.

- Incorporate the mitigation actions into the implementation plan.

I particularly like the second one. A SWOT analysis is most useful when it leads to action. Simply identifying weaknesses or threats doesn't change anything. By adding mitigation actions, the SWOT becomes a planning tool rather than just an analysis.

I'm also curious about your comment:

"I have a reason to wait..."

My first thought is that you're deliberately delaying engagement until the platform and core materials are ready. If that's your reasoning, it makes sense—you only get one first impression, and having a functioning website, a clear service definition, and professional materials makes that first contact much stronger.

Let's hear your reasoning, though. It may affect where "Produce user and client engagement materials" sits in the priority order.

That makes sense, and I think it's worth distinguishing between a personal readiness criterion and a project dependency.

From a project perspective, you could start engaging users now. But you've decided that you want to reach a certain weight before becoming the public face of WIMS. That's a personal decision about when you feel ready to represent the service.

Rather than treating it as procrastination, you can make it an explicit planning assumption.

For example:

User and client engagement will commence once the initial platform is operational and the project lead is satisfied that the service and personal presentation are ready for public launch.

Or more simply for your internal plan:

Delay active user and client engagement until personal readiness and core platform deliverables have been achieved.

That way the delay is intentional, not accidental.

It also suggests splitting the work into two tasks:

July

- Produce the engagement materials (flyer, handout, poster).

- Define the engagement strategy.

- Prepare the website and contact channels.

August (or when ready)

- Begin active engagement with potential users and clients.

- Gather initial feedback.

- Refine the service based on early interactions.

This has another advantage. You're not waiting to prepare—you're only waiting to launch. By the time you reach your target weight, all the supporting material is already complete, so you can begin engaging people immediately.

That's a much stronger position than delaying everything until you feel ready.