### WIMS Master Plan allocating time left to project

#### Project Structure

The six major project work streams (deliverables) are:

- WIMS Book (WBK)

- WIMS Educational Platform (WEP)

- WIMS Educational Content (WEC)

- WIMS Practical Theory (WPT)

- WIMS Community Engagement (WCE)

- WIMS Communications (WCM)

#### Project Calendar

- The Project Weeks (R) sheet is the authoritative project calendar.

- The Master Plan references the Project Calendar rather than calculating weeks.

#### PQ1 Objective

The primary objective for PQ1 is:

- Complete the WIMS Educational Platform (R1.3) by the end of Q1.

#### PQ1 Remaining Effort

From today to the end of PQ1:

- 55 Project Days remain.

Allocation:

| Work Stream | Remaining Project Days |
| --- | --- |
| WIMS Educational Platform | 33 |
| WIMS Book | 5 |
| WIMS Educational Content | 4 |
| WIMS Practical Theory | 4 |
| WIMS Community Engagement | 4 |
| WIMS Communications | 5 |
| Total | 55 |

#### Planning Assumption from Q2

Once WEP R1.3 is complete:

- The platform is considered operational.

- From Q2 onwards, allocate:

  - 1 Project Day per month for WIMS Educational Platform maintenance and enhancements.

No further assumptions or allocations have been made beyond this point.

Enjoy your rest. We'll continue one step at a time when you're ready.