I think this captures the discussion well while keeping it focused on WIMS.

# Week 1 Review (7–13 July)

## What Was Achieved

### WIMS Foundation

Week 1 demonstrated that a stable WIMS platform requires more than website implementation. During development it became clear that the educational content also required a defined structure.

As a result, development effort was reprioritised towards completing the WIMS baseline documentation, including:

- WIMS Service Definition

- WIMS Platform Definition

- WIMS Platform Implementation

- WIMS Content Structure Definition

This established a much stronger foundation for future platform development and releases.

### Lessons Learned

Content is part of the platform.

A stable educational platform requires both a stable technical structure and a stable content structure. Defining the content architecture became a prerequisite for implementation.

Communication follows content.

It became clear that public communication should support an established educational platform rather than precede it. Articles, presentations, YouTube videos and informal posts will be more effective when they direct users to existing educational resources.

The WIMS voice emerged naturally.

During content development, a conversational mentoring style emerged which better reflects the Weight Insight Mentoring Service than traditional instructional or marketing approaches. This provides a consistent voice for future educational content.

## Planned Activities Deferred

The following activities were intentionally deferred while completing the WIMS baseline documentation:

- June Fasting Report HTML conversion.

- Flyers and posters.

## Work Started

The following activities were started but remain in progress:

- Master Plan update.

- Book Structure Definition.

# Week 2 Priorities

### 1. Complete the Master Plan (Highest Priority)

Establish the operational baseline for WIMS and record the lessons learned from Week 1.

### 2. Complete the June Fasting Report

- HTML conversion.

- Presentation.

- Publication-ready educational resource.

### 3. Website Review

Carry out the first weekly review including:

- Website analytics.

- Client enquiries and emails.

- User observations.

- Evidence collected during the week.

### 4. Define the WIMS Spreadsheet

Produce a formal definition describing:

- Purpose.

- Scope.

- Functionality.

- Role within the WIMS mentoring service.

### 5. Marketing Review

Review current promotional activities including:

- Business card distribution.

- Flyer/poster progress.

- Early evidence of public engagement.

### 6. Book Structure

Continue defining the structure of the first WIMS book using the newly established content architecture.

Reading this back, I'd say Week 1 wasn't primarily an implementation week—it was a strategic foundation week. Week 2 naturally shifts towards implementation and publication, using the stronger baseline you've now established. I think that's a sensible progression and keeps the July objectives firmly on track.