## PW03 Planning Summary (20–24 July 2026)

| Objectives | Complete the June HTML Fasting Report. Begin the WIMS educational presentation. Establish the initial YouTube content creation process. Continue building the Project Office and Project Control framework. |
| --- | --- |
| Component Deliverables |  |
| PO – Project Office (8 hrs) | Complete Project Office documentation. Weekly reporting and website statistics review. |
| PC – Project Control (8 hrs) | Complete Configuration Management. Complete Baseline Management. Complete Implementation Planning. WEP – WIMS Education Platform (16 hrs) Complete HTML June Fasting Report. Begin introductory educational pages. Start the WIMS presentation. |
| WCM – WIMS Communications (4 hrs) | Produce initial YouTube educational content using the current recording setup. Prepare presentation materials. |
| PM – Planning & Reporting (4 hrs) | Complete Weekly Reporting. |
|  | Prepare PW04. |
|  | Prepare PM02. |

Working Philosophy

Work from the weekly one-page plan.

Record actual effort against component deliverables.

Keep solutions simple and evolve through use.

Focus on publishing and learning rather than perfection.

End of Week Outcome

By Friday PW03 should deliver:

✔ June HTML Fasting Report completed.

✔ Initial WIMS presentation started.

✔ First educational YouTube content produced.

✔ Project Office and Project Control documentation progressed.

✔ PW04 planned and ready to begin on Monday.