# WIMS Weekly Status Review

Week 2 Review (July 2026)

Project: WIMS – Weight Insight Mentoring Service

Reporting Period: Week 2, July 2026

Project Status: 🟢 Green

Prepared by: Project Office

Title: WIMS Weekly Status Review - PW03

Version: 1.0

Date: Month Year

Author: Graham Heap

Status: First Issue

Table Of Contents

1 Executive Summary	2

2 Overall Status	2

3 Major Achievements	3

4 Baseline Review	3

5 Key Lessons Learned	3

6 Risks	4

7 Opportunities	4

8 Planned Activities – Week 3	4

9 Project Health Assessment	5

10 Project Manager's Comments	5

11 References	6

12 Glossary	6

Document Revision History

| Document | Revision | Comment | Date |
| --- | --- | --- | --- |
| Initial Document Creation | 1.0 | First Issue | July 2026 |

# 1 Executive Summary

Week 2 marked an important transition in the WIMS project.

Rather than concentrating solely on technical implementation, significant effort was invested in strengthening project governance, configuration management and document control.

Although this resulted in fewer visible deliverables during the week, the work completed established the governance foundation required to support controlled implementation throughout the remainder of Q1.

A review of the WIMS – Service Definition and Implementation Plan V1.3 confirmed that the project remains fully aligned with the original baseline objectives.

Overall project status remains Green.

# 2 Overall Status

| Area | Status |
| --- | --- |
| Project Governance | 🟢 Ahead |
| Project Office | 🟢 Ahead |
| Configuration Management | 🟢 Ahead |
| Baseline Documentation | 🟢 Complete |
| Website Platform | 🟢 On Plan |
| Educational Platform | 🟢 On Plan |
| HTML Conversion | 🟡 In Progress |
| Educational Content | 🟡 In Progress |
| YouTube Channel | 🟢 On Plan |
| Overall Project | 🟢 Green |

# 3 Major Achievements

The principal achievements during Week 2 were:

- Project Office established as the central governance function.

- Directory structure rationalised.

- Baseline documentation reviewed and confirmed.

- Configuration management significantly improved.

- Critical implementation dependencies identified.

- Q1 implementation strategy refined.

- Governance documentation expanded.

- The project remains aligned with baseline objectives.

# 4 Baseline Review

The implementation review confirmed that no significant changes to project scope are required.

Instead, implementation has improved understanding of sequencing and governance.

The following observations were confirmed:

- A stable educational platform remains the primary Q1 objective.

- Website development supports the educational platform rather than representing the final deliverable.

- Educational publications, presentations and videos remain aligned with the original implementation strategy.

- The implementation philosophy of generating multiple outputs from a single piece of work remains valid.

# 5 Key Lessons Learned

Week 2 demonstrated that rapid technical development can outpace project governance.

The project therefore benefited from temporarily reducing implementation activity in order to establish:

- effective configuration management

- baseline identification

- document control

- improved project governance

This work is expected to improve implementation efficiency during the remainder of Q1.

# 6 Risks

Current Risks

| Risk | Status |
| --- | --- |
| Governance | Low |
| Technical Platform | Low |
| Educational Content Production | Medium |
| Schedule | Low |
| Scope Creep | Low |

No significant project risks require escalation.

# 7 Opportunities

Implementation during Week 2 identified several opportunities.

- Reuse of educational material across multiple media.

- Standardisation of document templates.

- Improved release planning.

- Better alignment between website, presentations and YouTube content.

- Stronger foundation for the first WIMS publication.

# 8 Planned Activities – Week 3

Primary objectives for Week 3 are:

- Continue HTML conversion.

- Expand the educational platform.

- Complete introductory educational pages.

- Produce supporting presentations.

- Continue development of the YouTube educational channel.

- Maintain configuration management discipline.

- Continue preparation for detailed August Work Breakdown Structures.

# 9 Project Health Assessment

The project is assessed as Green.

Implementation effort invested during Week 2 has strengthened governance without affecting project scope.

The Project Office, configuration management processes and refined implementation strategy provide a solid foundation for the controlled delivery of the remaining Q1 objectives.

The project is assessed as being slightly ahead of plan from a governance perspective and on plan for delivery of the September educational platform milestone.

# 10 Project Manager's Comments

Week 2 has been one of consolidation rather than rapid expansion.

While fewer visible deliverables were completed than originally anticipated, the project has matured significantly through the establishment of improved governance, configuration management and implementation planning.

The review confirms that the project remains fully aligned with the baseline implementation plan and is well positioned to accelerate delivery during the coming weeks.

# 11 References

Heap, G. (2026). June 2026 fasting report: Weight management as measurement and a feedback system: A reflective, data-led personal case study (September 2025–January 2026).

Project Management Institute. (2025). A guide to the Project Management Body of Knowledge (PMBOK® Guide) (8th ed.). Project Management Institute.

# 12 Glossary

Adapt

Baseline

Book

Client

Educational Platform

Fasting

Fasting Cycle

Feasting

Insight

Intervention

Know Thyself

Learn

Measurement

Mentoring

Service

Trend

User

Weight Insight

Weight Insight Mentor

Website

Working Definitions

Baseline – The initial reference point against which future progress or change is measured.

Insight – A meaningful understanding developed through measurement, learning and adaptation.

Weight Insight Mentor – A mentor who helps individuals better understand their own weight-change journey through education and evidence-informed guidance.