# Weight Insight Mentoring Service Definition

WIMS - Service Definition and Implementation Plan

Title: WIMS Definition

Version: 1.0

Date: June 2026

Author: Graham Heap

Status: Draft

Table Of Contents

1 Purpose of the document	4

1.1 Purpose of WIMS	4

2 Summary of  WIMS (Weight Insight Mentoring Service)	5

2.1 Know Thyself	5

2.2 Measure	5

2.3 Learn	5

2.4 Adapt	6

2.5 Project Direction	6

3 Project Overview	7

3.1 Project Goal/Objective	7

3.2 Project Scope	7

3.3 Project Purpose and Business Case	8

3.4 Project Objectives	8

3.5 Project Scope	8

3.6 Project Phased Delivery	8

3.6.1 Current Foundation Phase	8

3.6.2 Historical Documentation	9

3.6.3 Community Development	9

3.6.4 GitHub	9

3.7 Development Planning	10

3.8 Deliverables	10

3.9 Key Stakeholders, Roles, and Responsibilities	12

3.10 Project Milestone	13

3.11 Assumptions	13

3.12 Constraints	13

3.13 High-Level Risks	13

4 Appendix 1 - WIMS Book Structure	14

4.1 Foundations	14

4.2 Understanding Weight	14

4.3 The WIMS Framework	14

4.4 Practical Application	14

4.5 Real Life	14

4.6 The Future	14

5 Appendix 2 - WIM Service - Phase Development	15

5.1 WIM Phase 1 - Understand Thyself	15

5.2 WIM Phase 2 - Measure	15

5.3 WIM Phase 3 - Learn	15

5.4 WIM Phase 4 - Adapt	15

6 Appendix 3 - Risk Assessment	16

6.1 LinkedIn Profile	16

6.2 Informal SWOT Analysis	16

6.3 Strengths	16

6.3.1 Weaknesses	16

6.3.2 Opportunities	16

6.3.3 Threats	17

6.3.4 Potential Competition	17

6.3.5 Key Reputation Risks	19

6.3.6 Key Validation Questions	19

7 Appendix 4 - Detailed Planning Framework	20

7.1 Work Plan for July 2026 to June 2027	20

7.2 Scope Management	21

7.3 Monthly Planning	21

8 Planning for Action - Action The Plan!	21

9 Workstreams	22

9.1 Educational Platform Development	22

9.1.1 Human Biology	22

9.1.2 Scientific Literature	22

9.1.3 Working Theories	23

9.1.4 Experimental Programme	23

9.1.5 Community Development	23

9.1.6 Communications	24

9.1.7 Book Development	24

9.2 Programme Reviews	24

9.3 Growth Gates	24

9.4 Human Biology Research Strategy	24

9.5 Overall Philosophy	25

9.6 Development Notes – Human Biology Educational Strategy	25

10 Appendix 5 - Strategic Stakeholder Development	26

10.1 Stakeholder Philosophy	26

10.2 Stakeholder Groups	26

10.2.1 Platform Users	26

10.2.2 Professional Clients	26

10.2.3 Academic Community	26

10.2.4 Human Health Organisations	27

10.2.5 Publishing Partner	27

10.2.6 Technology Partners	27

10.2.7 Community Contributors	27

10.2.8 Future Strategic Partners	27

10.3 Stakeholder Development Principles	28

11 References	28

# 1 Purpose of the document

This document defines the Weight Insight Mentoring Service (WIMS) that combines the strategic development and implementation of the WIM Service.

The document is the combination of the development of a strategic service and the implementation planning of that service for July 2026 to June 2027.

An initial minimal viable service (MVS) currently exists as a website: www.ths-wim.com and introduces this service and provides user information resources and contact details for the mentoring role.

There are two types of customers identified for this service - users of the website and clients who may want mentoring.

## 1.1 Purpose of WIMS

To build a stable WIMS ecosystem supporting long-term education, research, mentoring, and community engagement, culminating in the publication of the first WIMS book by July 2027 (See Appendix 1 - Book structure).

An initial Minimal Viable Service (MVS) currently exists as a website - www.ths-wim.com was made operational in June 2026.

The (MVS) resources platform introduces the concept of a Weight Insight Mentor (WIM) and is based on the June 2026 Fasting Report [Heap, 2026], which provided the overall philosophy of the WIM Service: Know Thyself, Measure, Learn and Adapt.

Currently the platform allows users to access the June 2026 Report, provides a Google Sheet which allows for weight tracking and goal setting. In addition, it allows users to contact the author in the capacity of a Weight Insight Mentor.

This document outlines the strategic development of this service and provides an implementation plan for phased delivery for the next 12 months with the focus on producing a book by July 2027 which defines the WIM Service and Weight Insight Mentoring role.

# 2 Summary of  WIMS (Weight Insight Mentoring Service)

## 2.1 Know Thyself

The core philosophy of WIMS is rooted in self-awareness. Many people struggling with weight control feel confused, frustrated, or discouraged. The site should help them develop a clearer understanding of where they are now, how they arrived there, and what realistic progress looks like.

The content should be written in a relatable, accessible style rather than an academic or technical one.

Users should feel that they are learning from someone who has travelled a similar path and has spent years studying and experimenting with different approaches.

Help people develop insight, confidence, and understanding around weight change and how their lifestyle

impacts their weight.

The WIMS philosophy begins with the principle of **Know Thyself**.

Every individual is unique. Genetics, biology, life experiences, environment, habits, family influences and other personal factors all contribute to how each person responds to lifestyle choices.

As scientific understanding develops, additional factors, such as the gut microbiome, may also help explain individual differences.

Rather than assuming that a single approach is suitable for everyone, WIMS encourages individuals to observe themselves, measure meaningful outcomes,

learn from their own experiences and adapt their behaviour accordingly.

Human Biology and the Scientific Literature provide valuable supporting knowledge that may help explain these observations,

but they do not replace personal observation.

The purpose of WIMS is not to prescribe a universal solution,

but to help individuals develop a better understanding of themselves through evidence-informed observation, measurement, learning and adaptation.

## 2.2 Measure

Measurement remains central to the entire service.

The website (http://www.ths-wim.com) will explain why measurement matters, what should be measured, and how to record data consistently. The weight-tracking spreadsheet will be one of the key practical tools offered as a good example on the website.

A step-by-step guide will be developed to teach users how to use the spreadsheet effectively and how to interpret the information it provides.

The emphasis is not on reacting to daily fluctuations but on gathering meaningful information over time so that patterns can be identified and understood.

## 2.3 Learn

The website will become an educational platform containing articles, reports, guides, videos, and educational material.

The June Fasting Report is viewed as a foundation document from which many future resources can be developed.

Future content will include both practical and educational topics. Examples include blood sugar, insulin, metabolism, glycogen, fasting, energy balance, weight fluctuations, weekly averages, behaviour change, habit formation, sleep, stress, exercise, and long-term maintenance.

Each article or video will help visitors build their understanding step by step. The aim is to create a coherent body of knowledge rather than a collection of unrelated posts.

YouTube videos will complement the written material by explaining concepts in an accessible way and linking back to the website resources.

## 2.4 Adapt

The ultimate goal is to help and support people to make informed choices based on what they learn from the educational platform and from their own weight experiments and experience.

The framework of: Know Thyself, Measure, Learn, and Adapt provides a continuous improvement cycle that can be applied regardless of the specific dietary or lifestyle approach being followed.

The website, videos, spreadsheet, reports, and mentoring services all support this same process.

Over time, users may begin by reading articles and using the spreadsheet, then progress to watching videos, asking questions, and eventually seeking one-to-one client mentoring support.

The mentoring service is viewed as a natural extension of the educational material rather than the primary purpose of the website, however the intention is to present value to the user and good reasons to engage for client paid one on one mentoring. The expectation is that it will be an online service only.

## 2.5 Project Direction

The website will act as the central hub containing educational resources, reports, guides, downloads, videos, and contact information.

The immediate goal is to launch an initial minimal viable service in June 2026 has been achieved.

The longer-term vision includes a growing library of educational content, a YouTube channel, mentoring services, and eventually a book based on the accumulated articles, reports, videos, and practical experience.

Weight Insight Mentor Service will develop into an educational platform centred on the principles of:

- Know Thyself

- Measure

- Learn

- Adapt

The website (https://ths-wim.com) will serve as the hub for this educational platform articles, guides, videos, reports, downloads, and mentoring.

The June Fasting Report (2026) demonstrates the application of the tracking spreadsheet and presents real data demonstrating effective weight loss over a period of 6 months.

The spreadsheet is a practical tool.

The videos are the teaching medium.

Mentoring is the personal support layer.

The next section applies, where appropriate, the standard project management techniques from PMI (PMPOK, XXXX) to the implementation of the WIM Service.

# 3 Project Overview

WIMS - Weight Insight Mentoring Service

Project Name - WIMS - Resources Platform and Mentoring Service

Project Manager - Graham Heap

Project Sponsor - Graham Heap

(This is a scope statement)

The ongoing development of the current website and evolving educational platform should only be released when there is genuine growth. Avoid releasing minor changes simply because they have been completed.

Each release should represent a meaningful improvement that users can appreciate. Development should always be based on features that are known to be deliverable rather than optimistic promises.

A detailed project planning framework is presented in Appendix 4.

## 3.1 Project Goal/Objective

## 3.2 Project Scope

A minimal viable service (MVS) website (http://ths-wim.com) exists and was published in June 2026.

The basic one page website introduces the WIMS Service and provides the following resources:

- The June 2026 Fasting Report (Heap, 2026)

- A Google Sheet for tracking, goal settings of the users current weight and allows them to set a weight loss plan for periods in January - December 2026.

The ongoing development of the website to evolve into an educational platform is the initial focus of this document and the expectation is that by September 2026 a stable educational platform will exist which will provide sufficient resources to inform new and current users to be able to apply the basic principles of WIMS to their own situation and will allow for the operational addition of new materials.

This educational platform will essentially consist of technical improvements, articles, videos, presentations, research, experiments, mentoring processes, client journeys, templates, feedback mechanisms, early adopter engagement, content development, and positioning, all integrated into a single educational program.

## 3.3 Project Purpose and Business Case

In the traditional sense of a business case, there is not a defined market or user base estimation, or business case developed.

The author believes that sufficient demand for this service currently exists.

## 3.4 Project Objectives

Build a stable WIMS education platform by September 2026

Deliver the first WIMS book by July 2027.

Support long-term education, research, mentoring, and community engagement

## 3.5 Project Scope

High-Level Project Description

This project aims to establish a comprehensive WIMS ecosystem, integrating various educational and developmental components, and culminating in the publication of a foundational book. It will move through distinct phases to ensure a structured and coherent output, fostering long-term engagement and sustainability.

Scope

In Scope

Out of Scope

## 3.6 Project Phased Delivery

### 3.6.1 Current Foundation Phase

Immediate priorities include:

Platform

- Spreadsheet improvements.

- Improved menu system.

- Website navigation.

Content

- Convert the June 2026 report into HTML.

- Keep the PDF unchanged as the permanent historical record.

- Produce the report presentation.

- Produce the WIMS presentation.

- Produce the "Role of a WI Mentor" presentation.

Marketing

- Begin YouTube rollout.

- Prepare business cards.

- Prepare flyers.

Community

- Community feedback page.

- Release Notes page.

- Vision and Mission page.

### 3.6.2 Historical Documentation

The June 2026 PDF should remain unchanged.

Reason:

It represents a permanent record of thinking now.

The HTML version becomes an accessible presentation of the same document rather than replacing it.

Future reports build on previous work rather than rewriting history.

### 3.6.3 Community Development

Users should be encouraged to contribute ideas.

Good ideas that fit the vision of WIMS can be incorporated into future releases.

Release Notes should acknowledge features inspired by community suggestions.

Contributors may be recognised by name if they wish, otherwise anonymously.

The objective is to create a collaborative platform where users help shape future development.

### 3.6.4 GitHub

A public GitHub repository should be considered.

Benefits include:

- Demonstrating development skills.

- Demonstrating project management.

- Showing continuous development.

- Teaching software engineering approaches.

- Supporting future collaboration.

- Acting as a professional portfolio.

Release Categories

Platform Releases

Major functional improvements to WIMS.

Content Releases

Reports, presentations, and educational material.

Marketing Releases

YouTube, website updates, LinkedIn, flyers, business cards.

## 3.7 Development Planning

Planning should operate at several levels.

Vision
Long-term direction.

Roadmap
Major workstreams over the coming months.

## 3.8 Deliverables

Website development and content

Ongoing operational support post-initial launch

Software solutions

Marketing and sales activities beyond initial positioning and early adopter engagement

Article and video production

Funding for independent research projects not directly tied to WIMS content

Presentation materials and templates

Standalone projects not integrating into the single educational program

Research and experimental initiatives

Mentoring process design and implementation

Client journey mapping and optimization

Development of templates

Feedback mechanisms and early adopter engagement strategies

Content development for the WIMS ecosystem

Positioning strategy for WIMS

First WIMS book

Initial release of WIMS version one

WIMS ecosystem foundation

Defined and implemented mentoring process

Documented client journey

Standardized templates

Operational feedback mechanisms

Engaged early adopter community

WIMS positioning strategy document

Comprehensive content development for all ecosystem components

- June Fasting Report 2026

- Presentation of the June Fasting Report

- Video content for YouTube based on the Fasting Presentation Report

- Book summary after a year of operations

- WIMS website version 1

- Content Ideas for blogs and YouTube podcasts:

- weight fluctuations

- averages and trends

- fasting

- behaviour change

- measurement

- sustainable progress

- WIM Toolbox

- Nutrition

- Activity

- Behaviour

- Recovery

- Timing

- Mentoring Materials

- onboarding questionnaire

- lifestyle audit

- consultation structure

- mentoring notes template

- follow-up template

WIM resource library

Tool Box

Nutrition

Mediterranean-style eating.

Reducing processed foods.

Increasing vegetables.

Protein strategies.

Activity

Walking.

Cycling.

Interval training.

Resistance training.

Behaviour

Eating slowly.

Meal planning.

Habit formation.

Environmental design.

Timing

Meal timing.

Intermittent fasting.

Structured eating windows.

## 3.9 Key Stakeholders, Roles, and Responsibilities

Project Sponsor

Provides project authorization, secures resources, and ensures alignment with business objectives

Project Manager

Leads project planning and execution, manages risks, and communicates with stakeholders

Content Users

Client Engagement

End-users of WIMS Ecosystem

Provide user requirements and feedback for WIMS components (Source: uploaded artifacts)

Early Adopters

WIMS Community

Provide initial feedback and validate concepts for early releases (Source: uploaded artifacts)

Mentors / Mentoring Participants

WIMS Community

Engage in and provide feedback on mentoring processes and content (Source: uploaded artifacts)

Content Contributors

WIMS Project Team / External Experts

Develop and refine articles, videos, and presentations for the ecosystem (Source: uploaded artifacts)

Research Contributors

WIMS Project Team / External Researchers

Conduct and integrate research findings into the ecosystem (Source: uploaded artifacts)

Experiment Contributors

WIMS Project Team / External Participants

Design and execute experiments relevant to WIMS principles (Source: uploaded artifacts)

## 3.10 Project Milestone

Target Milestone 				Completion Date

MVS Initial Release of WIMS V1.0  		June 2026

First WIMS Book Publication 		July 2027

## 3.11 Assumptions

Multiple outputs (website, software, articles, etc.) can be effectively coordinated and integrated into a single, cohesive WIMS educational platform.

The phased development model (Understand Thyself, Measure/Clarify, Learn/Structure) will effectively support progression from initial understanding to a structured and mature WIMS offering.

All workstreams, whether directly or indirectly, will contribute to the successful publication of the WIMS book and the overarching educational program objective. (Source: uploaded artifacts - inferred)

Required human and financial resources will be available as needed to meet project timelines and deliverables.

## 3.12 Constraints

Fixed strategic deadlines: Initial release of Version One by end of June 2026.

A stable platform and delivery content process in place by September 2026.

Fixed strategic deadlines: First WIMS book publication by July 2027.

All workstreams must remain aligned to the single educational program objective, preventing fragmentation.

## 3.13 High-Level Risks

Risk assessment is an outstanding activity and this work is presented in Appendix 3.

# 4 Appendix 1 - WIMS Book Structure

## 4.1 Foundations

Why Another Weight Management Book?

The WIMS Philosophy

Measured Discipline

The Role of Awareness

## 4.2 Understanding Weight

Energy Balance

Human Biology and Metabolism

Behaviour and Habits

Why Diets Often Fail

## 4.3 The WIMS Framework

Know TheySelf

Measure

Learn

Adapt

## 4.4 Practical Application

Fasting

Food

Exercise

Feasting

## 4.5 Real Life

Case Studies

Common Mistakes

Long-term Success

## 4.6 The Future

Ethical Application of AI and Human Mentoring

The Future of WIMS

# 5 Appendix 2 - WIM Service - Phase Development

## 5.1 WIM Phase 1 - Understand Thyself

Lifestyle audit.

Weight history.

Previous attempts.

Current habits.

Goals.

## 5.2 WIM Phase 2 - Measure

Daily weight.

Possibly waist measurements.

Possibly activity tracking.

Observation period.

## 5.3 WIM Phase 3 - Learn

What patterns emerge?

What seems most likely to help?

Where is the biggest opportunity?

## 5.4 WIM Phase 4 - Adapt

For example:

Eat more slowly.

Stop sugary drinks.

Walk daily.

Add vegetables to lunch.

Reduce evening snacking.

Then observe.

# 6 Appendix 3 - Risk Assessment

## 6.1 LinkedIn Profile

Founder & Concept Developer, WIMS (Weight Insight Mentor Service)

Developing WIMS, a resource platform and mentoring service focused on helping people better understand the relationship between lifestyle choices, behaviour, wellbeing, and weight through self-awareness, measurement, learning, and adapting their behaviour based on their own understanding.

The current website represents the initial Minimum Viable Service (MVS), providing access to personal research findings, practical tools, and optional one-to-one mentoring support. The service is being actively developed based on client feedback and ongoing research. Further information is available at www.ths-wims.com.

## 6.2 Informal SWOT Analysis

## 6.3 Strengths

Genuine and authentic personal experience.

Built on observation, measurement, learning, and adaptation.

Resource platform combined with mentoring service.

Non-prescriptive approach.

Encourages self-awareness and informed decision-making.

Practical resources already available (report, spreadsheet, website).

Low-cost Minimum Viable Service already operational.

Human-led rather than technology-led.

Trust-based rather than sales-driven.

Strong alignment between philosophy and development approach.

### 6.3.1 Weaknesses

Service may be difficult to explain quickly.

Visitors may not immediately understand the difference between WIMS and coaching, dieting, or fasting programmes.

Currently based largely on personal experience and observations.

Limited evidence beyond founder experience.

Dependent on Graham's time for mentoring.

The value proposition may not yet be obvious to strangers.

Potential perception that resources could be replaced by free apps or online content.

Website and service offering are still evolving.

### 6.3.2 Opportunities

Friend-to-friend referrals.

Resource sharing within existing social networks.

Growth through trust and recommendations rather than advertising.

Expansion of resources and mentoring offerings.

Development of group mentoring or support options.

Collection of client feedback to improve service.

Building case studies and testimonials over time.

Establishing a niche around weight insight rather than weight-loss programmes.

### 6.3.3 Threats

Being misunderstood as a diet programme.

Being misunderstood as a fasting programme.

Being misunderstood as a coaching business.

Being misunderstood as a medical or nutritional advice service.

Difficulty differentiating from free apps and online resources.

Limited scalability of one-to-one mentoring.

Competitors adopting similar concepts if proven successful.

Public scepticism regarding personal-experience-based approaches.

Lack of clear differentiation could limit referrals.

### 6.3.4 Potential Competition

Weight-Loss Programmes

Commercial slimming organisations.

Structured diet programmes.

Meal-plan-based services.

Likely criticism:

People need structure, not reflection.

People need a programme, not insight.

Dieticians and Nutritionists

Registered nutrition professionals.

Clinical nutrition services.

Likely criticism:

Personal experience is not a professional qualification.

Limited scientific evidence.

Sample size of one.

Doctors and Medical Professionals

GP advice.

Clinical obesity services.

Likely criticism:

Where is the evidence base?

How are medical risks managed?

What safeguards exist for clients with health conditions?

Health Coaches

Lifestyle coaches.

Wellness coaches.

Behaviour-change coaches.

Likely criticism:

We already help people change behaviour.

What is unique about WIMS?

Fasting Communities and Advocates

Online fasting groups.

Fasting coaches.

Likely criticism:

WIMS is not focused enough on fasting.

Fasting should be the primary solution.

Weight-Loss Apps

Tracking apps.

Habit apps.

Calorie counting apps.

Likely criticism:

None directly.

Risk of similar features being incorporated into existing platforms.

Informal Support Networks

Friends.

Family.

Accountability partners.

Peer support groups.

Likely criticism:

Why pay for mentoring when a trusted friend can help?

Counterpoint:

WIMS provides structure, tools, observations, and a mentoring framework that most informal support relationships do not.

### 6.3.5 Key Reputation Risks

Why is a project manager offering a weight-related service?

Being mistaken for a medical professional.

Being mistaken for a nutritionist or dietician.

Being perceived as a fasting evangelist.

Over-promising outcomes.

Being challenged on the evidence base.

Service demand exceeding mentoring capacity.

### 6.3.6 Key Validation Questions

Would I recommend this website to a friend if I had not built it?

Would I feel comfortable giving the business card to someone I care about?

What makes people share the website with others?

What do people think WIMS is after a 30-second visit?

What value does WIMS provide beyond a free app?

What value does WIMS provide beyond a knowledgeable friend?

Can visitors clearly distinguish between the resource platform and the mentoring service?

Does the service solve a real problem that people recognise and value?

# 7 Appendix 4 - Detailed Planning Framework

## 7.1 Work Plan for July 2026 to June 2027

| Workstream | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Platform Development | X |  |  |  |  |  |  |  |  |  |  |  |
| Human Biology | X |  |  | X |  |  | X |  |  | X |  |  |
| Scientific Literature |  |  |  | X |  |  | X |  |  | X |  |  |
| Theory Development |  |  |  | X |  |  | X |  |  | X |  |  |
| Applied Experiments | X |  |  | X |  |  | X |  |  | X |  |  |
| Community Development |  |  |  | X |  |  | X |  |  | X |  |  |
| Communications | X |  |  | X |  |  | X |  |  | X |  |  |
| Book Development | X |  |  | X |  |  | X |  |  | X |  |  |
| Monthly Programme Review | X | X | X | X | X | X | X | X | X | X | X | X |

Key

Q1 - Jul 26, Aug 26, Sep 26

Q2 - Oct 26, Nov 26, Dec 26

Q3 - Jan 27, Feb 27,  Mar 27

Q4 - Apr 27, May 27, Jun 27

The primary deliverable is the publication of the first WIMS book in July 2027.

The work streams developed during the year should contribute directly or indirectly towards this objective.

The website, software, articles, videos, presentations, research and experiments are not independent projects; they are interconnected workstreams contributing to a single educational programme.

The implementation plan is organised by:

- Time (monthly milestones)
- Workstreams
- Outputs

Each month should produce meaningful outputs across several workstreams.

## 7.2 Scope Management

WIMS initial service will focus on understanding weight change, human biology, and the author's documented observations and educational resources.

Broader topics relating to healthy lifestyles and the wider health effects of fasting are recognised as important areas for future development but remain outside the current programme scope until sufficient evidence, educational content and research have been developed.

## 7.3 Monthly Planning

Each month has clearly defined milestones.

Monthly milestones naturally decompose into weekly missions.

Weekly missions naturally decompose into daily tasks.

Planning, therefore, follows a simple hierarchy:

| Vision → | WIMS Plan 2026/2027 → | Monthly Milestones → | Weekly Missions → | Daily Tasks Action |
| --- | --- | --- | --- | --- |

Planning for Action - Action The Plan!

# 8 Workstreams

| Work stream | Purpose | Output |
| --- | --- | --- |
| Educational Platform Development | Develop and maintain the WIMS software platform. | Website improvements Reporting User interface Data collection Visualisation GitHub development |
| ### Human Biology | Develop educational material explaining Human Biology from first principles. | Educational articles Book chapters Website content Presentations Teaching videos |
| ### Scientific Literature | Develop a comprehensive understanding of current scientific knowledge. | Literature reviews Research summaries Reference library Research Spotlight articles University and researcher profiles |
| ### Working Theories | Develop conceptual models explaining observed biological behaviour |  |

Human Biology and Scientific Literature

The Human Biology and Scientific Literature workstreams support the WIMS philosophy by providing additional knowledge that may help explain observed behaviour. They are intended to improve understanding rather than define the purpose of the project.

WIMS is not a medical, nutritional or dietetic service. Where appropriate, articles may summarise established scientific knowledge from publicly available and appropriately referenced sources to help explain biological concepts and observations. Such material is clearly distinguished from WIMS observations, working theories and self-experiments.

The primary purpose of WIMS remains to encourage individuals to understand themselves through observation, measurement, learning and adaptation.

### 1.3

Purpose

.

Activities

- Record observations

- Develop explanations

- Compare with published biology

- Refine theories

Outputs

- Working models

- Discussion articles

- Future research questions

### 8.1.4 Experimental Programme

Purpose

Design and conduct structured self-experiments.

Initial Focus (2026)

Observation only.

Formal experimental design develops after sufficient biological understanding has been established.

Outputs

- Experimental protocols

- Case studies

- Data analysis

- Research reports

### 8.1.5 Community Development

Purpose

Develop an active learning community.

Outputs

- User feedback

- Mentoring

- Questions and Answers

- Community-inspired improvements

## 8.2 Communications

Purpose

Communicate the WIMS project through education, marketing and customer engagement, making research findings and project outputs accessible to current and future users.

Activities

Produce educational content.

Promote the WIMS service.

Develop marketing materials.

Maintain digital communication channels.

Engage with users and clients.

Gather feedback to support continuous improvement.

Typical Outputs

Educational Publications

Articles

Reports

Presentations

Educational resources

Digital Content

Website content

Blog posts

Videos

Social media content

Marketing Materials

Business cards

Flyers

Posters

Brochures

Promotional graphics

Customer Engagement

Mentoring support

Public talks

Workshops

Community discussions

Client feedback

Frequently Asked Questions

Guiding Principle

One piece of work should generate multiple outputs across educational publications, digital content, marketing materials and customer engagement activities.

### 8.2.1 Book Development

Purpose

Produce the July 2027 publication.

The book develops continuously throughout the programme rather than being written at the end.

Articles, presentations, Human Biology lessons, literature reviews and experiments all become future chapters.

## 8.3 Project Reviews

At the end of each month, review:

- What outputs were produced?

- Which workstreams are advanced?

- What was learned?

- Which working theories changed?

- Which growth gates have been reached?

- What are next month's priorities?

## 8.4 Growth Gates

Development progresses through capability rather than dates.

Typical gates include:

- Foundation Complete

- Educational Foundation Complete

- Scientific Foundation Complete

- Experimental Readiness

- Publication Readiness

Each gate defines the conditions required before the next stage begins.

## 8.5 Human Biology Research Strategy

The long-term emphasis shifts from software development towards education, Human Biology and evidence-based investigation.

The educational progression becomes:

- Learn the Human Biology.

- Understand the current scientific literature.

- Develop working theories.

- Design structured experiments.

- Collect evidence.

- Publish observations as carefully documented case studies.

This approach separates established scientific knowledge from personal observations while encouraging continuous learning.

## 8.6 Overall Philosophy

The WIMS programme is not a collection of independent projects.

It is a coordinated educational ecosystem.

Every workstream supports the others.

Every month produces tangible outputs.

Every output contributes towards the July 2027 book.

The book is therefore not a separate project but the natural culmination of a year's structured learning, software development, research, communication and community engagement.

## 8.7 Development Notes – Human Biology Educational Strategy

As the WIMS platform evolves, the emphasis will increasingly shift from software development towards education, scientific literacy and evidence-based learning.

The long-term objective is not simply to teach fasting, but to help people understand Human Biology.

Educational content will generally follow a layered approach:

- Introduce the relevant Human Biology in clear, accessible language (approximately A-Level to first-year university standard).

- Summarise the current scientific understanding by referencing review papers, meta-analyses and other high-quality evidence.

- Introduce leading researchers, research groups and universities working in the field, encouraging readers to explore the original scientific literature.

- Present WIMS observations and self-experiments as clearly identified case studies, distinguishing personal experience from established scientific evidence.

Research topics will extend beyond fasting and include hydration, water balance, electrolytes, glycogen storage, digestion, nutrition, exercise, metabolism and other aspects of Human Biology.

The guiding principle is to help people understand how the human body works through a combination of sound biology, current scientific evidence and carefully designed, repeatable self-experiments.

# 9 Appendix 5 - Strategic Stakeholder Development

## 9.1 Stakeholder Philosophy

Stakeholder engagement is a continuous workstream within the WIMS Programme rather than a one-time activity. Relationships should develop alongside the maturity of the platform. The objective is to build long-term, mutually beneficial partnerships that strengthen the educational mission of WIMS. Stakeholder engagement should be purposeful, aligned with the values of the programme and appropriate to the current stage of development.

## 9.2 Stakeholder Groups

### 9.2.1 Platform Users

Purpose

Develop an active learning community.

Typical Activities

- Gather feedback.

- Improve usability.

- Encourage participation.

- Support continuous improvement.

### 9.2.2 Professional Clients

Purpose

Provide mentoring, consultancy and educational services.

Typical Activities

- Demonstrate the platform.

- Deliver presentations.

- Build long-term client relationships.

### 9.2.3 Academic Community

Purpose

Strengthen the scientific and educational quality of WIMS.

Potential Partners

- Universities.

- Academic departments.

- Individual researchers.

- Research groups.

Typical Activities

- Follow current research.

- Reference published work.

- Engage respectfully with the academic community.

- Identify opportunities for future collaboration.

### 9.2.4 Human Health Organisations

Purpose

Develop relationships with organisations whose objectives align with improving long-term Human

Health.

Potential Activities

- Educational partnerships.

- Public engagement.

- Collaborative initiatives.

- Community outreach.

### 9.2.5 Publishing Partner

The publication of the July 2027 book represents one of the major strategic objectives of the programme.

Rather than approaching publishers only after the manuscript is complete, relationships should be developed progressively throughout the programme.

Activities may include:

- Identifying publishers specialising in Human Biology, health, science and popular science.

- Understanding their publishing philosophy.

- Reviewing submission requirements.

- Studying successful publications.

- Developing a professional book proposal.

- Building a credible educational platform that demonstrates the value of the project.

The objective is to establish a long-term publishing partnership rather than simply seeking publication of a single manuscript.

### 9.2.6 Technology Partners

Purpose:  Support the continued development of the WIMS platform.

Potential Areas

- Software development.

- Artificial Intelligence.

- Educational technology.

- Open-source collaboration.

### 9.2.7 Community Contributors

Purpose: Encourage users to contribute ideas that improve the platform.

Contributions may include:

- Feature suggestions.

- Educational topics.

- Research questions.

- User feedback.

Appropriate recognition should be provided where contributors wish to be acknowledged.

### 9.2.8 Future Strategic Partners

As the programme matures, additional stakeholder groups may include:

- Investors.

- Sponsors.

- Educational charities.

- Professional organisations.

- International collaborators.

These relationships should only be pursued where they support the long-term educational vision of WIMS.

## 9.3 Stakeholder Development Principles

- Build relationships gradually.

- Focus on long-term trust rather than short-term opportunities.

- Seek partnerships that align with the educational mission.

- Ensure relationships provide value to both WIMS and the stakeholder.

- Allow stakeholder engagement to grow naturally as the programme matures.

Stakeholder management should therefore be viewed as a long-term programme of relationship building that supports the continued development, credibility and impact of WIMS.

# 10 References

Heap, G. (2026). June 2026 fasting report: Weight management as measurement and a feedback system: A reflective, data-led personal case study (September 2025–January 2026).

Project Management Institute. (2025). A guide to the Project Management Body of Knowledge (PMBOK® Guide) (8th ed.). Project Management Institute.