# WIMS Project Baseline Report

## Work Completed To Date (June 2026) - Summary

June 2026 established the foundation of the Weight Insight Mentoring Service (WIMS).

The month moved the project from an idea/concept stage into an operational Minimal Viable Service (MVS) with:

- Defined service model

- Implementation plan

- Working website platform

- Initial content

- Technical environment

- Marketing materials started

- Project standards initiated

# June 2026 Completed Work Register

| Work Completed | Status |
| --- | --- |
| Review of Fasting Report completed | Completed Week 1 June |
| WIMS concept/idea created | Completed |
| Weight Insight Mentoring Service definition created | Completed |
| WIMS Implementation Baseline Plan completed | Completed |
| Initial Minimal Viable Service identified | Completed |
| Website www.ths-wim.com implemented | Live |
| Initial WIMS website content released | Completed |
| Project test area established | Completed |
| General scratch/development area established | Completed |
| HTML standards initiated | Started / under review |
| CSS standards initiated | Started / under review |
| PHP standards initiated | Started / under review |
| Website development approach established | Started / under review |
| Business cards designed/produced | Initial release completed |
| Flyers/posters initiated | In progress |

# Standards Work Carry Forward

Target completion: End July 2026

| Item | Status |
| --- | --- |
| HTML coding standards | Complete review |
| CSS coding standards | Complete review |
| PHP coding standards | Complete review |
| Website structure standards | Complete review |

# Cost Tracking Model

Direct Costs

| Cost Item | Tracking Method |
| --- | --- |
| Website hosting | Actual hosting fees |
| Domain/platform costs | Actual cost |
| Business cards | Printing/design cost |
| Flyers | Paper + ink costs |
| Posters | Paper + ink costs |
| AI support tools | Subscription/service cost |
| Other software/services | Actual cost |

## Labour Cost Model

Assumption:

| Item | Value |
| --- | --- |
| Hourly rate | €50/hour |
| Working week | 40 hours |
| Working month | 160 hours |
| Equivalent monthly value | €8,000/month |

## Effort Categories To Track

| Category | Description |
| --- | --- |
| Research | Learning, investigation, evidence review |
| Planning | Service definition, implementation planning |
| Content Development | Reports, articles, book, presentations |
| Technical Development | Website, HTML, CSS, PHP |
| Marketing | Flyers, posters, business cards |
| Administration | Reporting, reviews, project control |
| Business Development | Business plan, service model |

# Additional Costs/Effort Rua Suggests Capturing 🦊

(Not adding work — just accounting categories)

| Item | Reason |
| --- | --- |
| Computer/equipment usage | Business resource consumption |
| Electricity | Development environment cost |
| Internet | Required operating cost |
| Software licences | Production support |
| Training/research time | Intellectual investment |
| Testing/review time | Quality control |
| Feedback sessions | Market validation effort |
| Document storage/backups | Project infrastructure |

# Business Interpretation

June was not a “thinking month”.

June created the foundation assets:

Concept → Definition → Plan → Platform → First Release

July focus:

Stabilise → Measure → Prepare → Improve

🤣 Rua verdict:

The funniest discovery:

You accidentally created a startup-style project record while trying to have an “easy life”.

Master Human: “I’ll just do a small website.”
Reality: “Here is your service definition, platform, implementation plan, cost model and release cycle.”

🧞‍♂️ Returning to bottle before suggesting a finance dashboard. 😂