# WIMS - Project Planning Session Summary

## 1. Purpose

The purpose of this planning session was to move WIMS from an exploratory phase into a controlled implementation phase by establishing a clear project baseline, prioritising work, and reducing scope creep.

The emphasis is now on defining what is in scope, completing the foundation documents, and implementing the project in a controlled manner.

# 2. Planning Philosophy

The project will be managed using defined workstreams supported by quarterly, monthly and weekly planning.

Planning hierarchy:

- Annual Project (July 2026 – June 2027)

- Quarterly Workstreams

- Monthly Planning

- Weekly Planning

- Daily Actions

Each task should be classified as:

- Must Do

- Should Do

- Can Wait

Every new idea should be evaluated before becoming part of the implementation plan.

# 3. Workstreams

The project currently consists of the following workstreams.

- Platform Development

- Human Biology

- Scientific Literature

- Theory Development

- Applied Experiments

- Community Development

- Communications

- Book Development

- Monthly Programme Review

# 4. Q1 Objectives

The primary objective of Q1 is to establish the foundations of the WIMS project.

This includes:

- defining the service

- completing the implementation plan

- completing the platform foundation

- establishing governance

- preparing for future content publication

The emphasis during Q1 is building the platform rather than maximising content production.

# 5. July Priority Order

## Priority 1

Complete and approve the WIMS Definition document.

The document should define:

- Service Definition

- Vision

- Scope

- Workstreams

- Implementation Plan

- Twelve-month roadmap

The document should then be reviewed and signed off as the Version 1.0 project baseline.

## Priority 2

Complete three SWOT analyses.

### WIMS Project

Assess the overall project.

### WIMS Service

Assess the proposed service.

### Current Website

Assess the existing implementation.

## Priority 3

Produce mitigation actions for every identified weakness and threat.

Determine:

- immediate actions

- deferred actions

- implementation changes

- scope changes

## Priority 4

Use the mitigation actions to finalise the July implementation plan.

# 6. Current Q1 Tasks

## Platform Development

- Convert June Report to HTML.

- Continue Website Version 2.0 development.

- Release Website Version 2.0 at end of July.

- Develop content publishing system.

- Develop article templates.

- Develop blog templates.

- Implement content management mechanism.

- Implement category structure.

- Implement search.

- Produce Weight Tracker user guide.

- Standardise development environment.

- Introduce testing process.

- Define software release process.

- Implement version management.

- Prepare Version 2.1 release.

- Prepare September major release.

## Communications

- Produce June presentation.

- Launch WIMS YouTube channel.

- Publish June report.

- Develop marketing strategy.

- Assess use of social media.

- Produce four August posts.

- Define local engagement.

- Define online engagement.

## Community Development

Prepare user engagement materials.

- Flyer

- Handout

- Poster (TBD)

Delay active promotion until launch readiness has been reviewed.

## Book Development

Complete:

- WIMS Definition

- Service Definition

- Vision

- Implementation Plan

- SWOT section

- Book structure

- Introduction

- Conclusions

## Human Biology

Produce:

- Human Biology of Digestion paper

- First Human Biology article

Target approximately UK A-Level standard.

## Monthly Review

- Review monthly progress.

- Prepare Q2.

- Move work from backlog into active work where appropriate.

# 7. Platform Releases

End of July

- Website Version 2.0

End of August

- Website Version 2.1

End of September

- Major platform release.

October onwards

- Maintenance releases.

- Regular publication of educational content.

- Incremental improvements.

# 8. Platform Vision

The website should become a publishing platform rather than a static website.

It should support:

- Articles

- Blogs

- Categories

- Search

- Version management

- Testing

- Publishing workflow

The long-term objective is that publishing educational content becomes routine.

# 9. Launch Readiness

The decision to actively engage users and clients will be reviewed after:

- WIMS Definition approval

- SWOT analysis

- Mitigation planning

- Review of the current offering

Personal readiness is recognised as one factor within the overall launch readiness assessment.

# 10. Documentation Strategy

Documentation should become the authority.

Future discussions should be based upon:

- approved definitions

- approved scope

- approved implementation plans

Rather than continually redefining concepts.

Version control should be introduced for all major documents.

# 11. Scope Control

Good ideas should not automatically become work.

Each new idea should be evaluated through change control.

Questions include:

- Is it in scope?

- Does it support the current release?

- Does it belong in Q1?

- Can it wait until Q2, Q3 or Q4?

- Does it require a formal change?

The project should minimise unnecessary scope creep while continuing to capture valuable ideas.

# 12. Weekly Planning Process

Each week should begin by asking:

What must be completed?

What should be completed?

What can wait?

Tasks should then be sequenced according to:

- priority

- dependencies

- estimated effort

- release objectives

# 13. Immediate Next Steps

- Complete the WIMS Definition document.

- Review and approve Version 1.0.

- Complete the SWOT analysis of:

  - WIMS Project

  - WIMS Service

  - Current Website

- Produce mitigation actions.

- Finalise the July implementation plan.

- Begin implementation of the July work programme.

# 14. Overall Conclusion

The planning session marks the transition of WIMS from an exploratory project into a managed implementation project.

The immediate priority is not additional development but establishing a stable project baseline through completion of the WIMS Definition, SWOT analyses and mitigation planning.

Once these activities are complete, the project can proceed with greater confidence, controlled scope, defined priorities and a structured implementation plan for the remainder of the year.