# WIMS Master Project Plan

## Planning Approach and Spreadsheet Structure

Version: 0.1 Draft
Date: July 2026
Input Baseline: WIMS Service Definition and Implementation Plan V1.3

# 1. Introduction

The WIMS Master Project Plan provides the operational planning and control framework required to deliver the Weight Insight Mentoring Service implementation programme.

The WIMS Service Definition and Implementation Plan defines the vision, purpose, scope, deliverables and strategic implementation approach.

The Master Project Plan converts this implementation approach into a controlled execution framework consisting of:

- Workstream planning

- Deliverable tracking

- Milestone management

- Risk management

- Monthly reviews

- Action planning

The Master Project Plan will be maintained as a living spreadsheet rather than a static document.

# 2. Project Control Structure

The planning approach follows the established WIMS planning model:

Vision
↓
WIMS Service Definition and Implementation Plan
↓
Master Project Plan
↓
Monthly Milestones
↓
Weekly Missions
↓
Daily Tasks
↓
Action

The purpose of the Master Project Plan is to ensure that all activity remains aligned with the development of the WIMS educational platform and the publication of the first WIMS book.

# 3. Master Project Plan Spreadsheet

The Master Project Plan workbook will contain the following control sheets.

# 4. Sheet 1 — Project Dashboard

## Purpose

Provide a single overview of the current project status.

## Content

- Project information

- Current phase

- Key milestones

- Overall project health

- Major risks

- Current priorities

## Key Milestones

| Milestone | Target |
| --- | --- |
| Initial MVS Release | June 2026 |
| Service Definition and Implementation Plan Baseline | July 2026 |
| Stable WIMS Platform | September 2026 |
| First WIMS Book Publication | July 2027 |

# 5. Sheet 2 — Master Project Schedule

## Purpose

Provide the primary project execution plan.

The schedule will manage all project workstreams, activities and deliverables.

## Structure

| Field | Purpose |
| --- | --- |
| ID | Unique reference |
| Workstream | Area of activity |
| Deliverable | Expected output |
| Activity | Required work |
| Start Date | Planned start |
| End Date | Planned completion |
| Status | Current progress |
| Priority | Importance |
| Notes | Supporting information |

# 6. Project Workstreams

The Master Project Plan will manage the following workstreams:

## Educational Platform Development

Purpose:

Develop and maintain the WIMS platform.

Outputs:

- Website improvements

- User experience improvements

- Resource management

- Release management

- GitHub repository

## Educational Content Development

Purpose:

Create the educational foundation of WIMS.

Outputs:

- Articles

- Reports

- Presentations

- Website content

- Videos

## Human Biology

Purpose:

Develop accessible educational material explaining relevant human biology.

Outputs:

- Learning articles

- Book chapters

- Educational resources

## Scientific Literature

Purpose:

Develop understanding of established scientific knowledge.

Outputs:

- Literature reviews

- Research summaries

- Reference library

## Practical Experiments and Case Studies

Purpose:

Document observations and learning.

Outputs:

- Personal experiments

- Data analysis

- Reports

- Case studies

## Community Development

Purpose:

Develop user engagement and feedback.

Outputs:

- User feedback

- Questions and answers

- Community improvements

## Communications

Purpose:

Communicate project outputs.

Outputs:

- Website updates

- YouTube content

- Social media

- Marketing material

## Book Development

Purpose:

Produce the first WIMS publication.

Outputs:

- Book structure

- Draft chapters

- Review versions

- Final publication

Target:

July 2027

# 7. Sheet 3 — Stable WIMS Platform Plan

## Purpose

Manage delivery of the first major project milestone.

Target:

Stable WIMS Platform — September 2026

## Platform Deliverables

Website:

- Improved navigation

- Improved structure

- Download resources

- Release notes

- Feedback process

Content:

- June 2026 Report HTML version

- WIMS presentation

- Weight Insight Mentor presentation

- Initial educational articles

Service:

- Mentoring process

- Client journey

- Supporting templates

- Feedback approach

Technical:

- Version control

- GitHub repository

- Release process

- Backup process

# 8. Sheet 4 — Deliverable Register

## Purpose

Track all project outputs.

Each piece of work should support multiple outputs where possible.

Example:

Research activity

may produce:

- Article

- Presentation

- Video

- Book content

## Register Fields

| Field | Purpose |
| --- | --- |
| Deliverable ID | Tracking |
| Name | Output |
| Workstream | Owner area |
| Type | Article, video, report etc |
| Target Date | Delivery |
| Status | Progress |

# 9. Sheet 5 — Risk Register

## Purpose

Maintain active management of risks.

The initial risk register will be derived from:

- SWOT analysis

- Implementation risks

- Platform risks

- Project delivery risks

# Risk Categories

## Strategic Risks

Examples:

- WIMS misunderstood as a diet programme

- Value proposition unclear

- Lack of differentiation

## Educational Risks

Examples:

- Scientific credibility challenged

- Confusion between education and advice

- Evidence base misunderstood

## Operational Risks

Examples:

- Dependency on founder time

- Too many parallel activities

- Loss of focus

## Platform Risks

Examples:

- Poor user experience

- Technical issues

- Content growth becoming difficult to manage

# Risk Register Format

| Field | Purpose |
| --- | --- |
| Risk ID | Tracking |
| Description | Risk statement |
| Source | SWOT / Project / Platform |
| Probability | Likelihood |
| Impact | Effect |
| Rating | Priority |
| Response | Management action |
| Status | Open / Closed |

# 10. Sheet 6 — Monthly Review Log

## Purpose

Provide project governance.

At the end of each month review:

- What was delivered?

- Which workstreams progressed?

- What was learned?

- What changed?

- What risks changed?

- What are next month's priorities?

# 11. Summary

The WIMS Master Project Plan is the operational control framework for delivery of the WIMS implementation programme.

The Service Definition and Implementation Plan defines:

Why and What

The Master Project Plan manages:

How, When and Progress

The objective is not additional planning.

The objective is controlled execution leading to:

- Stable WIMS Educational Platform

- Growing educational content library

- Active community engagement

- First WIMS Book Publication — July 2027

Planning complete. Execution begins.