# WIMS Project Management Framework

Strategic Planning Summary – June 2026

1 Strategic Objective	2

2 Programme Philosophy	2

2.1 Programme Decision – Scope Management	3

2.2 Monthly Planning	4

3 Workstreams	5

3.1 Platform Development	5

3.1.1 Human Biology	5

3.1.2 Scientific Literature	5

3.1.3 Working Theories	6

3.1.4 Experimental Programme	6

3.1.5 Community Development	6

3.1.6 Communications	7

3.1.7 Book Development	7

3.2 Programme Reviews	7

3.3 Growth Gates	7

3.4 Human Biology Research Strategy	8

3.5 Overall Philosophy	8

4 Addendum – Strategic Stakeholder Development	9

4.1 Stakeholder Philosophy	9

4.2 Stakeholder Groups	9

4.2.1 Platform Users	9

4.2.2 Professional Clients	9

4.2.3 Academic Community	9

4.2.4 Human Health Organisations	10

4.2.5 Publishing Partner	10

4.2.6 Technology Partners	10

4.2.7 Community Contributors	10

4.2.8 Future Strategic Partners	11

5 Stakeholder Development Principles	11

Title: WIMS Programme Plan

Version: 1.0

Date: June 2026

Author: Graham Heap

Status: Approved

Work Plan for July 2026 to June 2027

| Workstream | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Platform Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Human Biology |  |  |  |  |  |  |  |  |  |  |  |  |
| Scientific Literature |  |  |  |  |  |  |  |  |  |  |  |  |
| Working Theories |  |  |  |  |  |  |  |  |  |  |  |  |
| Experimental Programme |  |  |  |  |  |  |  |  |  |  |  |  |
| Community Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Communications |  |  |  |  |  |  |  |  |  |  |  |  |
| Book Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Monthly Programme Review |  |  |  |  |  |  |  |  |  |  |  |  |

# 1 Strategic Objective

The primary deliverable is the publication of the first WIMS book in July 2027.

Everything developed during the year should contribute directly or indirectly towards this objective.

The website, software, articles, videos, presentations, research and experiments are not independent projects; they are interconnected workstreams contributing to a single educational programme.

# 2 Programme Philosophy

The programme is organised around three dimensions:

• Time (monthly milestones)
• Workstreams
• Tangible outputs

Each month should produce meaningful outputs across several workstreams.

## 2.1 Programme Decision – Scope Management

WIMS Version 1 will focus on weight management, Human Biology, and the author's documented observations and educational resources. Broader topics relating to healthy lifestyles and the wider health effects of fasting are recognised as important areas for future development but remain outside the current programme scope until sufficient evidence, educational content and research have been developed.

## 2.2 Monthly Planning

Each month has clearly defined milestones.

Monthly milestones naturally decompose into weekly missions.

Weekly missions naturally decompose into daily tasks.

Planning, therefore, follows a simple hierarchy:

Vision

↓

Annual Programme

↓

Monthly Milestones

↓

Weekly Missions

↓

Daily Tasks

# 3 Workstreams

## 3.1 Platform Development

Purpose

Develop and maintain the WIMS software platform.

Typical Outputs

- Website improvements

- Reporting

- User interface

- Data collection

- Visualisation

- GitHub development

### 3.1.1 Human Biology

Purpose

Develop educational material explaining Human Biology from first principles.

Typical Outputs

- Educational articles

- Book chapters

- Website content

- Presentations

- Teaching videos

### 3.1.2 Scientific Literature

Purpose

Develop a comprehensive understanding of current scientific knowledge.

Typical Outputs

- Literature reviews

- Research summaries

- Reference library

- Research Spotlight articles

- University and researcher profiles

### 3.1.3 Working Theories

Purpose

Develop conceptual models explaining observed biological behaviour.

Activities

- Record observations

- Develop explanations

- Compare with published biology

- Refine theories

Outputs

- Working models

- Discussion articles

- Future research questions

### 3.1.4 Experimental Programme

Purpose

Design and conduct structured self-experiments.

Initial Focus (2026)

Observation only.

Formal experimental design develops after sufficient biological understanding has been established.

Outputs

- Experimental protocols

- Case studies

- Data analysis

- Research reports

### 3.1.5 Community Development

Purpose

Develop an active learning community.

Outputs

- User feedback

- Mentoring

- Questions and Answers

- Community-inspired improvements

### 3.1.6 Communications

Purpose

Transform knowledge into accessible public content.

Outputs

- Blog posts

- Website articles

- YouTube videos

- Presentations

- LinkedIn articles

- Educational resources

One piece of work should generate multiple outputs across these communication channels.

### 3.1.7 Book Development

Purpose

Produce the July 2027 publication.

The book develops continuously throughout the programme rather than being written at the end.

Articles, presentations, Human Biology lessons, literature reviews and experiments all become future chapters.

## 3.2 Programme Reviews

At the end of each month, review:

- What outputs were produced?

- Which workstreams advanced?

- What was learned?

- Which working theories changed?

- Which growth gates have been reached?

- What are next month's priorities?

## 3.3 Growth Gates

Development progresses through capability rather than dates.

Typical gates include:

- Foundation Complete

- Educational Foundation Complete

- Scientific Foundation Complete

- Experimental Readiness

- Publication Readiness

Each gate defines the conditions required before the next stage begins.

## 3.4 Human Biology Research Strategy

The long-term emphasis shifts from software development towards education, Human Biology and evidence-based investigation.

The educational progression becomes:

- Learn the Human Biology.

- Understand the current scientific literature.

- Develop working theories.

- Design structured experiments.

- Collect evidence.

- Publish observations as carefully documented case studies.

This approach separates established scientific knowledge from personal observations while encouraging continuous learning.

## 3.5 Overall Philosophy

The WIMS programme is not a collection of independent projects.

It is a coordinated educational ecosystem.

Every workstream supports the others.

Every month produces tangible outputs.

Every output contributes towards the July 2027 book.

The book is therefore not a separate project but the natural culmination of a year's structured learning, software development, research, communication and community engagement.

# 4 Addendum – Strategic Stakeholder Development

## 4.1 Stakeholder Philosophy

Stakeholder engagement is a continuous workstream within the WIMS Programme rather than a one-time activity. Relationships should develop alongside the maturity of the platform. The objective is to build long-term, mutually beneficial partnerships that strengthen the educational mission of WIMS. Stakeholder engagement should be purposeful, aligned with the values of the programme and appropriate to the current stage of development.

## 4.2 Stakeholder Groups

### 4.2.1 Platform Users

Purpose

Develop an active learning community.

Typical Activities

- Gather feedback.

- Improve usability.

- Encourage participation.

- Support continuous improvement.

### 4.2.2 Professional Clients

Purpose

Provide mentoring, consultancy and educational services.

Typical Activities

- Demonstrate the platform.

- Deliver presentations.

- Build long-term client relationships.

### 4.2.3 Academic Community

Purpose

Strengthen the scientific and educational quality of WIMS.

Potential Partners

- Universities.

- Academic departments.

- Individual researchers.

- Research groups.

Typical Activities

- Follow current research.

- Reference published work.

- Engage respectfully with the academic community.

- Identify opportunities for future collaboration.

### 4.2.4 Human Health Organisations

Purpose

Develop relationships with organisations whose objectives align with improving long-term Human

Health.

Potential Activities

- Educational partnerships.

- Public engagement.

- Collaborative initiatives.

- Community outreach.

### 4.2.5 Publishing Partner

The publication of the July 2027 book represents one of the major strategic objectives of the programme.

Rather than approaching publishers only after the manuscript is complete, relationships should be developed progressively throughout the programme.

Activities may include:

- Identifying publishers specialising in Human Biology, health, science and popular science.

- Understanding their publishing philosophy.

- Reviewing submission requirements.

- Studying successful publications.

- Developing a professional book proposal.

- Building a credible educational platform that demonstrates the value of the project.

The objective is to establish a long-term publishing partnership rather than simply seeking publication of a single manuscript.

### 4.2.6 Technology Partners

Purpose:  Support the continued development of the WIMS platform.

Potential Areas

- Software development.

- Artificial Intelligence.

- Educational technology.

- Open-source collaboration.

### 4.2.7 Community Contributors

Purpose: Encourage users to contribute ideas that improve the platform.

Contributions may include:

- Feature suggestions.

- Educational topics.

- Research questions.

- User feedback.

Appropriate recognition should be provided where contributors wish to be acknowledged.

### 4.2.8 Future Strategic Partners

As the programme matures, additional stakeholder groups may include:

- Investors.

- Sponsors.

- Educational charities.

- Professional organisations.

- International collaborators.

These relationships should only be pursued where they support the long-term educational vision of WIMS.

# 5 Stakeholder Development Principles

- Build relationships gradually.

- Focus on long-term trust rather than short-term opportunities.

- Seek partnerships that align with the educational mission.

- Ensure relationships provide value to both WIMS and the stakeholder.

- Allow stakeholder engagement to grow naturally as the programme matures.

Stakeholder management should therefore be viewed as a long-term programme of relationship building that supports the continued development, credibility and impact of WIMS.